## 2019 GNC work plan
Global Nutrition Cluster (GNC) Work Plan, 2019-2020
| Activities: | 2019 | 2020 | Start | End | SAG contribution | Monitoring indicators (2019-202) | Costing Details | Amount needed for 2019 | Funded for 2019 | Gap for 2019 | Owner | Priority | Current situation, Dec 2018 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Strategic Priority 1: To provide operational support before, during, and after a humanitarian crisis to national coordination platforms to ensure quality and timely response
Outcome A: Response - platforms supported by GNC have the capacity to fulfil their role in coordination and information management (IM)
| Identify, maintain and deploy trained surge NCCs, IMOs to country clusters in the intial phase and critical periods of the emergency including RRT, TRRT, IRT and other mechanisms like SBP pool, NGOs, UN partner and support longer term recruitment based on countries need | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Number of RRT deployments - 8 Numebr of GNC-Ct deployments - 2 Number of SBP NCC and IMO deployments - 4 | Funding included under the outcome A1 | 0 | 0 | 0 | GNC -CT, TRRT | A
| Provide timely support to country clusters/sectors through GNC HelpDesk and GNC-CT deployments, including strategic support to HNO/HRP development and technical NiE support | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Number of GNC Ct deployments to country 5 Number of countries provided remote support through coordinatiojn helpdesk - 18 Number of countries provided IM helpdesk remote support - 10 Number of countries with HNO/HRP reviewed - 20 | Funding included under the outcome A1 | 0 | 0 | 0 | GNC -CT, TRRT | A
| Systematically advocate with country clusters/sectors on the regular implementation of CCPM and provide support in implementation, validation and follow up of the CCPM and its plan of action | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Number of countries CCPM conducted this year - 7 | GNC-CT to take on (GNC-Helpdesk mainly remotely) and cost for travel for validation workshop (1 person), included under helpdesk, other possible travel to be funded by countries | 0 | 0 | 0 | GNC -CT | A | Ongoing
| Adapt GNC coordination tools and training packages (partners, CC and IM packages) to include GBV and gender equality considerations and organise learning workshops in selected priority countries for national nutrition coordination members on integrating GBV into nutrition interventions. | 2019 | N/A | 2018-01-01 | 31/12/2018 | Not needed | Number of packages with included/reviewed GBV section - 3 | Staff time. Part of the AAH project funded by USAID, funding not included in the GNC workplan | 0 | 0 | 0 | GNC-CT/AAH/UNICEF | A | EMOPS GBV Specialist has reviewed GNC training packages and HRP tips and provided feedback
| Develop and host an online nutrition survey dashboard to collect and analyis SMART surveys from country level | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Funding secured in 2019 and implementation started - yes | As per the draft budget from ACF | 900000 | 0 | 900000 | GNC-CT and ACF Canada/ UNICEF
Outcome B: Preparedness – national coordination platforms supported by GNC have the capacity to react appropriately to emergencies
| Develop a list of minimum preparedness requirements and actions for coordination of NiE responses | 2019 | N/A | 2017-01-01 | 2017-12-31 | Review final draft | List of minimum preparedness actions developed | GNC Coordination helpdesk with UNICEF PD (how to, based on Peter's and Brenda's document) | 0 | 0 | 0 | GNC -CT/ UNICEF | B
| Assess national coordination platforms in preparedness for coordination of NiE responses against minimum preparedness requirements | 2019 | N/A | 2017-01-01 | 2017-12-31 | Not needed | Number of countries assessed -2 | GNC Coordination helpdesk with UNICEF PD (staff time) | 0 | 0 | 0 | GNC -CT/ UNICEF | B
| Identify list of GNC priority countries to roll-out the NiE response coordination preparedness | 2019 | N/A | 2017-01-01 | 2017-12-31 | Not needed | Number of countries identified - 4 | GNC Coordination helpdesk with UNICEF PD | 0 | 0 | 0 | GNC -CT/ UNICEF | B
Strategic Priority 2: Relevant Nutrition stakeholders (national and global) have the capacity to coordinate a quality and timely response.
Outcome A: Global - The pool of Nutrition personnel to support coordination and information management in response to humanitarian crises is sufficient to meet demand
| Ensure participation of SBP, UN agencies and NGOs in training events on cluster approach and IM for NCCs, IMOs | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Number of NCCs training - 1 Number of IMO trainings -1 Number of partner trainings - 3 Numbe rof government officials attended trainings - 30 | One NCC training in March - 30,000, one IMO training in March - 30,000, three country trainings (Bangladesh, DRC and Madagascar) - 15,000 each in Q1 and Q2, travel of the GNC staff 20,000 (missing) | 125000 | 105000 | 20000 | GNC -CT | A | Fully funded, RedR PCA and GNC-CT, but no money for the GNC staff travel
| Review and revise the GNC IM Toolkit, including to strengthen gap analysis mapping tools and systematically work with countries to implement them | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Number of tools revised - 26 | GNC IM helpdesk, CDC | 0 | 0 | 0 | GNC-CT, IM helpdesk, CDC | A | Ongoing
| Develop a mentoring package for the cluster IMOs and NCCs | 2019 | N/A | 2017-01-01 | 31/12/2018 | Review final draft | Package developed - yes Number of NCCs/IMOs mentored - 6 | RedR thorugh PCA | 70000 | 70000 | 0 | GNC-CT | B | Fully funded, RedR PCA and GNC-CT
Outcome B: National/Regional - Coordination mechanisms have the capacity to coordinate and meet their responsibilities in assisting affected populations in humanitarian crises
Activities:
1 | Conduct a local capacity mapping of coordination and IM functions and competencies in GNC priority countries | 2017-01-01 |  | 2017-01-01 | 2017-12-31 |  |  | role for NCC/IMOs in priority countries, with support from RRT NCCs and IMOs |  |  |  | RRT | A
2 | Organise and conduct training events to address capacity gaps in cluster/sector coordination and IM in priority countries, with specific focus on national capacities | 2017-01-01 |  | 2017-01-01 | 31/12/2018 |  |  | RedR - travel, annual basis |  |  |  | Red-R UK | A
3 | Develop action plans to reflect learning and monitor its implementation from training participants | 2017-01-01 |  | 2017-01-01 | 31/12/2018 |  |  | RedR - has action planning template that could be provided for use in other training sessions. Monitoring Implementation: should be done by NCCs, IMOs |  |  |  | Red-R UK | A
4 | Pilot a coaching support to coordination teams in priority countries based on needs identified against selected coordination competencies | 2017-01-01 |  | 2017-01-01 | 31/12/2018 |  |  | RedR - has done this previously,- mentoring with WASH cluster - could pilot something simliar for Nutrition cluster, annually - mentoring relationships of 3-6 months depending on needs |  |  |  | Red-R UK | A
Strategic Priority 3: To influence and advocate for improved, integrated and coordinated nutrition response during humanitarian crises
Outcome A: Nutrition Cluster/sector/working group is appropriately activated in new crises as per the nutritional needs of the affected population and the capacity of the hosting government
Activities:
1 | Develop a guidance on the rationale to activate Nutrition Cluster/Sector/WG based on a comprehensive analysis of all nutrition indicators (MN deficiencies, stunting, wasting, suboptimal IYCF practices etc) and aggravating factors (care practices, FSL, health and WASH), including decision tree | 2018-01-01 |  | 2018-01-01 | 2018-12-31 |  |  | Consultancy to review & develop guidance (30 days) |  |  |  | UNICEF | B
2 | Develop comprehensive dissemination plan and promote the application of the activation guidance in new emergencies through engagement with UNICEF RO, HQ and OCHA and partners including national Ministries | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time |  |  |  | GNC-CT | B
3 | Assess and document the effectiveness of the process and application of the guidance in newly declared emergencies | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | PCA to review & document effectiveness Travel to countries |  |  |  | ENN | B
Outcome B-1: Nutrition-sensitive objectives are included, implemented, monitored and evaluated in relevant cluster plans (WASH, Food Security and Health Clusters)
| Revise a training package on integration for nutirition outcomes and develop a facilitators guide | 2019 | N/A | 2017-01-01 | 2017-12-31 | Not needed | Training revised and awailable online - yes Facilitators guide developed - yes | PCA with RedR ongoing | 40000 | 40000 | 0 | ICNWG leading, by RedR through signed PCA | A | Ongoing, ready by February
| Roll-out the pilot inter-cluster training package at least in four priority countries and finalise the package | 2019 |  |  |  | Review of the concept note | Number of countries where integration for nutiriotn outcomes trainign conducted - 4 | 4 trainings: contract 32K, venue $1.5K x 4 = 6K Travel GNC : participation in 4 trainings (3K x 4 = 12K) , | 146000 | 20000 | 126000 | ICNWG, Integration Helpdesk travel | A | Only funding for one country
| Translation of the integration training package to French | 2019 | N/A |  |  | Not needed | Integration package translated to French - yes | PCA with RedR ongoing | 20000 | 20000 | 0 | RedR through PCA, ICNWG | A | Planned funded
| Establishment of the helpdesk on Integration to support country Health, WASH, Nutirition and FSAC Clusters with integration for nutrition outcomens | 2019 | 2020 |  |  | Review the ToR for the consultancy | Number of countries that have developed and implemented at least 50% of their integrated plans - 6 | 90,000 for a consultant for 12 months | 90000 | 0 | 90000 |  | A | No funding
| Documentation of case studies on integration for nutirition outcomes from three countires | 2019 | N/A |  |  | Review of the concept note | Numebr of case studies - 3 | 15,000*3 case studies, possibly PCA with ENN plus 5,000 travel cost | 50000 | 0 | 50000 | ICNWG and GNC-CT | B | No funding
| Monitor the number of HRP/ Flash appeals including nutrition sensitive interventions | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Not needed | Numebr of HRP/Flash Appeals including nutiriotn sensitive interventions - 4 | Integration helpdesk | 0 | 0 | 0 | Integration helpdesk | B | No funding
Outcome B-2: Infant and Young Child Feeding-in Emergencies (IYCF-E) and micronutrient interventions are systematically included, implemented, monitored and evaluated in crisis responses within the Nutrition Cluster and other relevant clusters (Food Security, WASH, Health, Shelter and non-food items (NFI), Camp Coordination and Camp Management (CCCM), Child Protection and Education Clusters)
Activities:
1 | Compile key messages/guidance/tools on IYCF-E | 2017-01-01 |  | 2017-01-01 | 2017-12-31 |  |  | updated list of guidance / French and Arabic documents/ question for the GNC CT what would be the product at the end of this. |  |  |  | SCI | B
2 | Disseminate key messages/guidance/tools on IYCF-E to key stakeholders (including donors, national gov'ts and local partners)and global platforms | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time |  |  |  | SCI | B
3 | Compile key messages/guidance/tools on MN | 2017-01-01 |  | 2017-01-01 | 2017-12-31 |  |  | Consultancy - 40 days |  |  |  | GAIN/ NI | B
4 | Disseminate key messages/guidance/tools on MN to key stakeholders(including donors, national gov'ts and local partners) and global platforms | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Designer for desktop publishing |  |  |  | GAIN/ NI | B
5 | Develop final GNC partners-agreed template on IYCF Joint Statement and disseminate through global platforms | 2017-01-01 |  | 2017-01-01 | 2017-12-31 |  |  | ENN person work time |  |  |  | ENN | A
6 | Develop and disseminate a step-by-step guidance on integration of IYCF-E and MND activities into the activities of other sectors/clusters | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | Consultancy - 40 days Validation meeting - 1 day meeting costs |  |  |  | UNICEF | A
7 | Develop and disseminate a decision making tool to determine context-appropriate NiE interventions for Nutrition and other relevant clusters for country adaptation in all humanitarian responses | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | Consultancy - 40 days Validation meeting - 1 day meeting costs |  |  |  | UNICEF | A
Supporting Objective 1: To help deliver the GNC priorities by engaging collectively and individually with a range of external stakeholders (other clusters, donors, CLA, development actors) to commit to working together in all relevant phases of the Humanitarian Programme Cycle (HPC) and humanitarian-development nexus to ensure improved coordination.
Intercluster Objectives. Outcome A: Joint needs assessment and analysis, and response planning frameworks (with relevant clusters) are adopted at country level
Activities:
1 | Develop a framework for joint analysis and prioritisation that includes information from other clusters/sectors such as WASH, Health and FSL to ensure that crisis-affected population needs are addressed | 2017-01-01 |  | 2017-01-01 | 2017-12-31 |  |  | Consultant costs |  |  |  | ICNWG and GNC-CT/ UNICEF | A
2 | Expand the existing membership of the ICNWG of FSL-Nutrition clusters to include representation from Global WASH and Health Clusters | 2017-01-01 |  | 2017-01-01 | 2017-12-31 |  |  | GNC-CT/partners staff time |  |  |  | ICNWG and GNC-CT/ UNICEF | A
Intercluster Objectives. Outcome B: Integrated country clusters plans are in place with measurable indicators that meet the range of affected populations’ needs
Activities:
1 | Pilot the framework in selected priority countries during the HNO/HRP processes | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | Travel costs |  |  |  | GNC-CT | B
2 | Document the process and lessons learned to influence the framework | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | PCA with ENN + act 2 of outcome C |  |  |  | ENN | B
3 | Develop a standardized tool to monitor integrated project, including indicators for measuring impact of nutrition-sensitive interventions and include it in the GNC IM tool kit | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | Consultant costs |  |  |  | ICNWG | A
Intercluster Objectives. Outcome C: Common operational frameworks address the needs of affected populations
Activities:
1 | Undertake joint field mission with other relevant cluster to support them in systematic analysis and inter-cluster integration | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | Travel cost |  |  |  | ICNWG and GNC-CT | A
2 | Document and widely disseminate processes and tools to support strong inter-cluster integration at the country level | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | See line 83 |  |  |  | ENN | A
3 | Contribute to the development of the common operational frameworks that address the needs of affected population in particular scenarios | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time |  |  |  | GNC-CT and GHC | A
Intercluster Objectives. Outcome D: Country coordination personnel support integrated action through clusters
Activities:
1 | Update and validate the existing FSL cluster training package of nutrition sensitive interventions to incorporate Health and WASH interventions | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time |  |  |  | ICNWG | A
2 | Pilot and evaluate the training package in selected priority countries | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | Travel costs |  |  |  | ICNWG | A
CLA Engagement Objectives. Outcome A-1: More predictable funding to maintain global coordination and IM capacities for all UNICEF-led clusters and its Area of Responsibility
| Maintain sustainable funding of core GNC positions: GNC Coordinator, GC Deputy Coordinator, two RRT NCC, two RRT IMOs and the GNC Coordination HelpDesk Officer | 2019 | 2020 | 2017-01-01 | 2017-12-31 | Not needed | Funding available for GNC Coordinator, GC Deputy Coordinator, two RRT NCC, two RRT IMOs and the GNC Coordination HelpDesk Officer | Staffing costs: GNC Coordinator, GNC Deputy, Two RRT NCC and two RRT IMO - 'GNC plans to have 4 RRT: 2 staff and 2 partners. 2 PCAs to support RRTs x 180K = $360 1 RRT is deployed 24-36 weeks a year (4-6 missions in total) Travel required for UNICEF RRTs: $50K x 2 = $100K Helpdesk: $131K contract | 1326000 | 1046000 | 280000 | GNC-CT, UNICEF and RRT partners | A | Funding missing for the two RRTs through partners and UNICEF RRT travel cost
CLA Engagement Objectives. Outcome A-2: Increased mainstreaming of country coordination and IM capacities in UNICEF
| Advocate with the CLA and UNICEF RO/Country offices for the establishment, resource allocation and recruitment of dedicated cluster coordination positions (NCC and IMO) | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Not needed | Number of additionla NCC/IMO dedicated position established this year - 2 | GNC-CT/partners staff time | 0 | 0 | 0 | UNICEF/GNC-CT | A | Ongoing
CLA Engagement Objectives. Outcome B: The CLA commits to addressing preparedness for coordination of nutrition in emergencies responses through regular programmes in non-cluster activated countries
| Review the existing CLA Preparedness Guidance for Nutrition Programming and incorporate the preparedness actions for coordination of NiE responses in non-cluster countries, Support UNICEF HQ and ROs in rolling-out the preparedness guidance in selected non-cluster countries | 2019 | 2020 | 2017-01-01 | 2017-12-31 | Not needed | 5 countries supported in putting in place preparedness actions | 30K PD technical capacity consultancy | 30000 | 30000 | 0 | UNICEF/GNC-CT | A
| Advocacy and support to countries on replication of recommendation from transition review | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Advocacy support | Percentage of countries in need of transtion support supported - 100% | Staff time |  |  | 0 | UNICEF/GNC-CT | A
CLA Engagement Objectives. Outcome C: UNICEF plays a leadership role in technical support, guidance and capacity
| Development of the communication strategy and action plan for the Global Technical Mechanism | 2019 | 2020 | 2018-01-01 | 2018-12-31 | Review and endorsement of the GTM workplan and communication plan | GTM 2 year work plan developed - yes Communication plan and materials developed - yes | Staff time, PCA with WV, ENN and instituational Contract. Fully funded through UNICEF PD, 430,000 | 430000 | 430000 | 0 | UNICEF | A
| Forming/ facilitating four priority Global Thematic WGs (CMAM, IFE, Assessments Techical Expertise, Cash) | 2019 | 2020 | 2018-01-01 | 2018-12-31 | Review of the TOR/ SOP on the engaegement of the GTWG | Number of GTWG working support to GTM 4 Number of products developed by GTM and GTWGs - 2 | Included in the above | 0 | 0 | 0 | UNICEF | A
| To put in place the KM system for the GTM | 2019 | 2020 | 2018-01-01 | 2018-12-31 | Not needed | IT system for GTM in place - yes Number of updates on GTM performance and experiences - 4 | Included in the above | 0 | 0 | 0 | UNICEF | A
| Mapping of existing technical resources for providing technical advice and expertise | 2019 | 2020 | 2017-01-01 | 2017-12-31 | Advocacy for more agencies to provide tech expertise and review of existing resources | Database of existing resources in place - yes Number of partners/ networks providing tech expertise to countries - 8 Global TWG on Tech Expertise in place and functioning - yes | Included in the above | 0 | 0 | 0 | UNICEF | A
| Development of a system for requesting technical advice and technical expertise | 2019 | 2020 | 2017-01-01 | 2017-12-31 | Not needed | Number of countries supported by the GTM - 22 Number of partners supported by the GTM - 44 | Included in the above | 0 | 0 | 0 | UNICEF | A
| Based on the identified NIE technical needs by the country link the country clusters/sectors with the Technical RRT Consortia to effectively and timely address the needs in Assessments, CMAM, micronutrients deficiencies, IYCF-E and SBC among all age groups including adults and elderly | 2019 | 2020 | 2017-01-01 | 31/12/2018 | Not needed | Number of Tech RRT deployments - 12 | 2019 - funding till March, in discussion for cost extension for 6 months | 800000 | 200000 | 600000 | UNICEF, TRRT | A
| Development of the NiE training for UNICEF staff and partners | 2019 |  | 2017-01-01 | 31/12/2018 | Not needed | Training is developed and available online - yes | Instutional Contracts | 290, 000 | 290000 | 0 | UNICEF | B
Donor-Cluster Partnership Objectives. Overall Outcome: Increased predictable and multi-year funding for programming for coordination
| As a IPC Steerign Committee member, provided technical support to the IPC Acute Malnutiriotn and IPC Food Security Secretariat and support roll out of IPC analysis to countries | 2019 | 2020 |  |  | Advocacy | Number of countries where IPC AM conducted - 5 in 2019, 2020 tbc | GNC Coordinator staff time | 0 | 0 | 0 | GNC-CT/ UNICEF | A | Ongoing
| Engagement with SUN and advocacy for closer HDN linkages and particiciate in UN Network and Global SUN gatherign Events | 2019 | 2020 |  |  | Advocacy | Number of SUN meetigns with GNC-Ct participation - 1 | GNC Coordinator staff time | 0 | 0 | 0 | GNC-CT/ UNICEF | A
| Engagement with Famine Action Mechanism (FAM) | 2019 | 2020 |  |  | Advocacy | Number of countries with nutrition as integral part of FAM -5; Number of FAM events attended by the GNC-CT or GNC partners where advocacy for nutiriton is included - 4 | GNC Coordinator staff time | 0 | 0 | 0 | GNC-CT/ UNICEF | A
| Maintain a list of neglkected nutiriton crises and support countries with advocacy to influence donors | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Support in identifying what neglected crisis means, review structure of the template, identification of countries, review of the drafts | List of the neglected crises/countries is available and updated every 6 month - yes Number of countries supported to develop an advocacy paper/event on neglected crises - 2 | GNC Coordination Helpdesk (funding under helpdesk) Design and printing of information products | 5000 | 0 | 5000 | GNC-CT/ UNICEF | B
| Provide snapshots/briefs on needs and gaps for on-going L3 crisis on quarterly basis | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Review the structure of the template, identification of countries, review of the drafts | Number of advocacy papers on L3 developed and shared - 2 | GNC Coordination Helpdesk (funding under helpdesk) Design and printing of information products | 5000 | 0 | 5000 | GNC-CT/ UNICEF | A
| Organise donor events (with SUN and or other potential donors) and leveraging existing events for nutirtion financing and advocacy (possibly based on the HDN six case studies and cash) | 2019 | 2020 |  |  | Review of the agenda and other event documents, selecting participants, representation at the event | Number of donor events organised - 2 | No funding, UNICEF can possibly support the evet | 30000 | 0 | 30000 | GNC-CT/ UNICEF and SUN and CALP | B
| Support country clusters/sectors in roll-out the advocacy toolkit to national platforms to ensure it is being used by clusters and donors to inform their dialogue for long-term predictable funding of NiE responses, including the establishment of a system to monitor the impact of advocacy | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Not needed | Number of countries developed advocacy startegy in 2019 - 3 | GNC Helpdesk | 0 | 0 | 0 | GNC-CT/ UNICEF | A
| Organise a country-sepcific side events during the GNC Annual Meetings | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Review of the agenda and other event documents, representation at the event | Number of side events organised - 1 | Included in the GNC meeting cost, but addiitonla funding iis needed for SSFA/PCA for preparation | 50000 | 0 | 50000 | GNC-CT/ UNICEF | A
Development Actors' Engagement Objectives. Overall Outcome: Countries prone to crises have included NiE in national nutrition development plans
Activities:
1 | Engage with the national nutrition platforms through SUN and others and influence the development of the national nutrition plans in priority countries that incorporate preparedness action for NiE interventions, including support for coordination capacities | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Travel to meetings |  |  |  | GNC-CT/ UNICEF | A
2 | Advocate with the GNR and SUN Secretariat for systematic inclusion, monitoring and reporting of the progress of inclusion of NiE preparedness actions into national nutrition plans | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Travel to meetings |  |  |  | GNC-CT/ UNICEF | A
Development Actors' Engagement Objectives. Intermediate Outcome A: Humanitarian actors contribute to multi-stakeholder platforms in crisis-prone countries
Activities:
1 | Advocate with the GNC partners and the SUN Secretariat for participation and membership of humanitarian partners in SUN platforms at global and country level | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Travel to meetings |  |  |  | GNC-CT/ UNICEF | A
2 | Define five key messages for partners' engagement with development platforms | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Design and printing of key messages Travel to meetings |  |  |  | GNC-CT/ UNICEF | A
3 | Identify specific workstreams for GNC partner engagement under SUN | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Travel to meetings |  |  |  | GNC-CT/ UNICEF | A
Development Actors' Engagement Objectives. Intermediate Outcome B: A GNC-SUN MoU for fragile and conflict affected states (FCAS) outlines respective commitments and is adopted by GNC partners
Activities:
1 | SUN and GNC MoU defining the points of engagement between SUN and GNC developed and signed | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time GNC-CT/partners staff time to review the MOU |  |  |  | GNC-CT/ UNICEF | B
2 | Map the countries with activated clusters or FCAS with potential cluster activations, who are willing to join the SUN movement | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time |  |  |  | WFP | B
3 | Ensure GNC involvement in UN Network and SUN global and regional meetings | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time Travel |  |  |  | GNC-CT/ UNICEF | A
Supporting Objective 2: To help deliver the GNC strategic priorities by strengthening internal ways of working in the GNC partnership
Outcome A: Partnerships and communications support the delivery of strategic priorities
| Conduct Annual GNC meetings | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Review of the agenda and other event documents, representation at the event, chairing | Number of meetings organised - 1 | 95K for Annual Meeting, 5 days (30K venue, - - 50k SSFA for technical support and 15K GNCT travel), plus 100 people x4,000 per person travel and staff time | 495000 | 430000 | 65000 | GNC-CT and ECHO | A
| Update and maintain the GNC website | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Not needed | New website functional and regularly updated - yet | LTA for the website (36,000) and hosting (10,000 a year) | 46000 | 36000 | 10000 | GNC-CT, IM helpdesk | A | Ongoing
| Organize need-focused teleconferences with 1) GNC partners, 2) NCC, 3) IMOs and 4) the RRT | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Not needed | Number of monthly NCC calls - 12 Number of GNC partners calls - 3 Number of RRT calls - 6 | GNC-CT/partners staff time, GNC Helpdesks | 0 | 0 | 0 | GNC-CT | A | Ongoing
| Maintain a platform for communication, experience exchange and feedback with country clusters (GNC HelpDesk on Coordination and IM)) | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Not needed | Number of months with GNC Coordinationa nd IM helpdesk operational - 12 | Included in the staff cost | 0 | 0 | 0 | GNC-CT | A | Ongoing. GNC HelpDesk is functioning
| Manage GNC Partnerships with RRT host agencies and other partners leading implementation of GNC workplan | 2019 | 2020 | 2017-01-01 | 2018-12-31 | Advocacy to partners | Number of partner projects funded not thorugh UNICEF as a part of the GNC workplan - 3 | GNC-CT/partners staff time | 0 | 0 | 0 | GNC-CT | A | Ongoing\
Outcome B: Responses are improved through the capture and application of learning
| Document case studies (HINI, cash and continuum of care, and HDN) | 2019 | N/A |  |  | Review ToRs, technical calls with consultns, feedback on the draft documents | Number of case studies documented - 3 on integration, 6 on HDN Number of position papers developed - 3 | 105K for consultancy to develop HDN guidance 90K for two consultant fee for 6 months each - field review and guidance development in consulation with global and six country partners plus travel 15K for six missions), 60K cash guidance (cash expert for 6 months), 60K HINI guidance (cash expert for 6 months), | 225000 | 0 | 225000 | GNC CT with SUN/ UNICEF for HDN GNC CT and GTM for HINI GNCCT and Calp for cash | A | Possibly 60,000 available for cash through UNICEF EMOPS, tbc next year
| To develop a two pager (checklist) on the process on how to agree on the scaling up on comprehesive nutrition interventions at country level | 2019 | N/A |  |  | Review draft | A checklist developed - yes Number of countrieds that have HINI package in place - 5 | UNICEF PD staff time | 0 | 0 | 0 | UNICEF | B
Outcome C: GNC is sufficiently well-resourced to deliver its strategic priorities
Activities:
1 | Develop, cost, allocate responsibilities for fundraising and implementation and monitor a two-year costed rolling workplan | 2017-01-01 |  | 2017-01-01 | 2017-06-30 |  |  | GNC-CT/partners staff time |  |  |  | SAG, GNC-CT | A
2 | Launch of the GNC Strategy and a two-year costed rolling workplan | 2017-01-01 |  | 2017-01-01 | 2017-10-31 |  |  | Meeting costs and travel |  |  |  | SAG, GNC-CT | A
3 | Organise regular donor briefing on the progress of workplan implementation and funding requirements/status | 2017-01-01 |  | 2017-01-01 | 2018-12-31 |  |  | GNC-CT/partners staff time and travel costs |  |  |  | SAG, GNC-CT | A
Note on M44: Ruth Situma: to work togther with UNICEF given the subsequent activities ( 6 & 7 below) are depedent on this
Note on M45: Ruth Situma: to work togther with UNICEF given the subsequent activities ( 6 & 7 below) are depedent on this
Note on M46: Ruth Situma: to work togther with UNICEF given the subsequent activities ( 6 & 7 below) are depedent on this
Note on M47: Ruth Situma: to work togther with UNICEF given the subsequent activities ( 6 & 7 below) are depedent on this