## Week 1-2
Background: The Coordination Performance Checklist is a simple tool designed to monitor progress of coordination arrangements, including cluster activation and implementation for the first three months after the declaration of a level 3 emergency or in other contexts after the activation of clusters. The checklist assesses the status of the cluster activation, staffing, core functions, and deliverables. It can be used as both an ongoing performance checklist as well as a management and reporting tool. The checklist can also be used to guide other coordination solutions like sectors or themmatic working groups. Directions: It is suggested that a checklist should be completed for each country cluster/sector per location (capital, province/region). Some sections of the checklist should be completed by global clusters/cluster lead agencies, while others need to be filled in by the country cluster/sector coordinator. The blue shaded areas indicate by when action should be completed. An 'X' should be added to the appropriate cell when an action has been completed, automatically changing the color to green (adding '0' will change the color to red = significant constrains; adding '1' will change the cell to yellow = constraints, deliverable / function will be implemented with delays). The checklist includes a column for comments to indicate required follow-up action and additional support or to explain significant delays in completing an action. Checklists should be completed/updated two weeks, one month and two months after the declaration of a level 3 emergency, and should be made available to both the global clusters/ cluster lead agencies as well as the RC/HC and HCT. After the three month period, a Coordination Performance Report should be used when there is more time available to assess the quality of cluster operations in relation to the commitments to the principles of accountability to affected populations and the six core functions of country clusters. ** The first 14 days are included in this tab. The following tabs record activities at 3-4 weeks and 5-12 weeks.
Leadership
DAYS
Action | Deliverable | Location of action focus | Lead | Timing | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Coments
IASC Principals (including GCLA) meet and determine level of emergency | Determination of Level 3 response status | Global | IASC Principals and CLA | within 48 hours | bar: DAYS 2
Global Cluster Lead Agency / Global Cluster deploys L3 capable sector/cluster coordinators as required | staff in place | Global | GCC + GCLA | within 72 hours
GCLA / Global Cluster deploys IM specialist(s) on 'no regrets' basis | staff in place | Global | GCC + GCLA | within 72 hours
GCLA and Global Cluster Partners deploy additional technical staff for needs assessment, strategic planning and elaboration of flash appeal | staff in place | Global | GCLA + Global Cluster Partners | within 72 hours
Global Cluster Lead Agency / Global Cluster provides briefing notes to the IASC Principal of GCLA on leadership arrangements, rapid response deployments and cluster/sector coordination mechanisms | briefing note | Global, consulting country and region | GCLA + GCC | in 7-10 days | bar: DAYS 10
Coordination
Action | Deliverable | Location of action focus | Lead | Timing | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Comments
Country office of GCLA reviews if there is a coordination gap for its sector | note of findings | Country | CLA | within 48 hours | bar: 2
HCT meeting where arguments are discussed for cluster / sector activation where there are gaps, including detail at subnational level and designation of (co-)leads | Verbal arguments in HCT meeting and record of meeting | Country | HCT + CLA | within 48 hours, review at 3 months | bar: 2
Cluster/sector inputs to MIRA Preliminary Scenario Definition | Sector needs analysis as input to the MIRA PSD | Country | cluster / sector IM + CC | within 72 hours
Cluster / sector coordinators identify priority projects and resource requirements for staffing, based on MIRA/PSD strategic response priorities, for initial CERF allocation | list of cluster / sector staffing requirements, prioritised project needs, estimated costs | Country | CC + Partners | within 72 hours
Cluster/sector (co) lead agency presents priority projects and cluster staffing requirements to HC, for initial CERF allocation by HC | list of cluster / sector staffing requirements and prioritised project needs, estimated costs | Country | HCT + CLA | within 72 hours
Core Function 1 - Provide platform to support service delivery | Activate cluster / sector coordination meetings, Meeting Agenda, minutes, actions points | Country | CLA + CC | within 72 hours, then daily for first two weeks and bi-weekly till 8 weeks | bar: 7; 14
Core Function 1 - A mechanism to avoid duplication | Establish 4W database | Country | IM | <72 hours, update as required | bar: 7
Core Function 2 - Sectoral needs assessment and gap analysis | Report on needs and gaps (for sector and as input to MIRA, initial strategic plan, initial flash appeal, MIRA report at 14 days, revised flash appeal, etc) | Country | CC + IM | <72 hrs, update within 5 days, further update <14 days | bar: 5; 14
Core Function 2 - Analysis for response, including cross cutting issues | Report on response analysis (for sector and as input to MIRA, initial strategic plan, initial flash appeal, MIRA report at 14 days, revised flash appeal, etc) | Country | CC | <72 hrs, update within 5 days, further update <14 days | bar: 5; 14
Core Function 2 - Prioritisation, grounded in response analysis | Defined priorities (also as input to MIRA PSD, HCT initial strategic plan, etc) | Country | CC + Partners | < 72 hours, update within 5 days | bar: 5
Accountability
Action | Deliverable | Location of action focus | Lead | Timing | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Comments
Core Function 3 - Develop sectoral plan | Sectoral plan, with objectives and indicators | Country | CC + Partners | within 5 days | bar: 5
Core Function 3 - cluster / sector coordinators provide input to the HC initial strategic plan | sector input to initial strategic plan covering the first 3 months, including objectives and indicators | Country | CC + Partners | as of day 3, within 5 days | bar: 5
Core Function 3 - cluster / sector coordinators review final draft Initial strategic plan | final feedback to the HCT initial strategic plan | Country | CC + CLA | within 5 days | bar: 5
Core Function 3 - Application and adherence to existing standards and guidelines | Promotion of standards and good practice | Country | CC + Partners | <72 hours and periodic update | bar: 5; 14
Core Function 3 - Clarify funding requirements | Cluster budgets in flash appeal, CAP, ERF/CHF, CERF | Country | CC + IM | as per document timeline | bar: 7
Core Function 4 - Identify Advocacy concerns | Input to HC/HCT messaging | Country | CC + IM | within 5 days and periodic as required | bar: 5; 14
Core Function 4 - Undertake advocacy activities on behalf of cluster / sector partners and affected population | Press release/Sitreps | Country | CC + Partners | at least twice per week for first two months | bar: 4; 8; 11; 14
Core Function 5 - cluster / sector coordinator reports to CLA on progress and achievements towards cluster / sector objectives, based on defined indicators | Cluster/sector response monitoring and progress report | Country | CC + IM | weekly as of day 7 | bar: 7; 14
Core Function 5 - Cluster Lead Agency reports to HC on progress and achievements towards cluster objectives, based on defined indicators | Cluster/sector progress report (as contribution to the humanitarian dashboard) | Country | CLA | weekly as of day 7 | bar: 7; 14
Core Function 5 - cluster / sector coordinator facilitates consensus among operational partners on incorporating core Commitments on Accountability to Affected Populations. | CAAP integrated in partner programming | Country | CC + Partners | as of day 5 | bar: 5

## Week 3-4
Coordination
Action | Deliverable | Location of action focus | Lead | Timing | Week 3 | Week 4 | Comments
Core Function 1 - Provide platform to support service delivery | Activate cluster / sector coordination meetings, Meeting Agenda, minutes, actions points | Country | CLA + CC | within 72 hours, then daily for first two weeks and bi-weekly till 8 weeks
Core Function 1 - A mechanism to avoid duplication | Establish 4W database | Country | IM | <72 hours, update as required
Accountability
Action | Deliverable | Location of action focus | Lead | Timing | Week 3 | Week 4 | Comments
Core Function 3 - Application and adherence to existing standards and guidelines | Promotion of standards and good practice | Country | CC + Partners | <72 hours and periodic update
Core Function 3 - Clarify funding requirements | cluster / sector budgets in flash appeal, CAP, ERF/CHF, CERF | Country | CC + IM | as per document timeline
Core Function 4 - Identify Advocacy concerns | Input to HC/HCT messaging | Country | CC + IM | within 5 days and periodic as required
Core Function 4 - Undertake advocacy activities on behalf of cluster / sector partners and affected population | Press release/Sitreps | Country | CC + Partners | at least twice per week for first two months
Core Function 5 - cluster / sector Coordinator reports to CLA on progress and achievements towards cluster / sector objectives, based on defined indicators | Cluster/sector response monitoring and progress report | Country | CC + IM | weekly as of day 7
Core Function 5 - cluster / sector Lead Agency reports to HC on progress and achievements towards cluster / sector objectives, based on defined indicators | Cluster/sector progress report (as contribution to the humanitarian dashboard) | Country | CLA | weekly as of day 7

## Week 5-12
Coordination
Action | Deliverable | Location of action focus | Lead | Timing | Month 2 | Month 3 | Comments
HCT meeting where arguments are discussed for cluster activation where there are gaps, including detail at subnational level and designation of (co-)leads | Verbal arguments in HCT meeting and record of meeting | Country | HCT + CLA | within 48 hours, review at 3 months
Core Function 1 - Provide platform to support service delivery | Activate cluster coordination meetings, Meeting Agenda, minutes, actions points | Country | CLA + CC | within 72 hours, then daily for first two weeks and bi-weekly till 8 weeks
Core Function 1 - A mechanism to avoid duplication | Establish 4W database | Country | IM | <72 hours, update as required
Accountability
Action | Deliverable | Location of action focus | Lead | Timing | Month 2 | Month 3 | Comments
Core Function 3 - Application and adherence to existing standards and guidelines | Promotion of standards and good practice | Country | CC + Partners | <72 hours and periodic update
Core Function 3 - Clarify funding requirements | cluster / sector budgets in flash appeal, CAP, ERF/CHF, CERF | Country | CC + IM | as per document timeline
Core Function 4 - Identify Advocacy concerns | Input to HC/HCT messaging | Country | CC + IM | within 5 days and periodic as required
Core Function 4 - Undertake advocacy activities on behalf of cluster / sector partners and affected population | Press release/Sitreps | Country | CC + Partners | at least twice per week for first two months
Core Function 5 - cluster / sector Coordinator reports to CLA on progress and achievements towards cluster / sector objectives, based on defined indicators | Cluster/sector response monitoring and progress report | Country | CC + IM | weekly as of day 7
Core Function 5 - cluster / sector Lead Agency reports to HC on progress and achievements towards cluster / sector objectives, based on defined indicators | Cluster/sector progress report (as contribution to the humanitarian dashboard) | Country | CLA | weekly as of day 7
Core Function 6 - Contingency planning /preparedness for recurrent disasters whenever feasible and relevant | Review existing contingency/preparedness plan and update as required (or develop new ones as required) | Country | CC + Partners | after 3 months, review every six months