## Preparedness measures
Imaginary country Zwantipolis |  |  | Done
Preparedness Actions (PAs) workplan |  |  | Deadline set/ongoing
To be initiated/delayed
| Preparedness Actions | Status | Due date/Timeframe | Responsible entity | Cost (USD)
1.Risk Analysis and Monitoring
MPAs
111 | To follow the national Meteorological Department and Flood Forecasting Centre bulletins |  | on a weekly basis, 2 months ahead of clyclone and monsoon season | The NIWG, which in turns shares highlights to the Nutrition partners
112 | To monitor the disease surveillance system of the national institute of Epidemiology Disease Control |  | on a monthly basis and on a weekly basis during emergencies | The NIWG, which in turns shares highlights to the Nutrition partners
113 | To consult with OCHA and refine the choice of indicators to monitor risk of outbreak of armed conflict |  | by end of Jan 2023 | The ERP task force
APAs
114 | To refine the set of advanced preparedness actions for Nutrition that must be trigered when Alert stage is reached for monitoring indicators |  | by end of Jan 2023 | The ERP task force
2.Building crisis scenario
MPAs
211 | To review challenges and lessons learned for past Nutrition emergency responses |  | done, and included in the draft ERP plan | The ERP task force
212 | To access the list of administrative areas expected to be impacted by flooding during the monsoon season |  | done, and included in the draft ERP plan | The NIWG
213 | To access to any available population data relative to different affected groups (IDPs, returnees, host communities, specific minorities, etc.), groups with specific needs including older people, people with disability. |  | by end of Jan 2023 | The NIWG
APAs
214 | For each medium to high risk, to derive a set of assumptions, anticipate plausible events, aggravating factors, the direction the situation will take and deduce impact and humanitarian consequences, predict duration of crisis |  | done, and included in the draft ERP plan | The ERP task force
215 | To calculate PIN for each scenario (risk-specific PIN) and for the duration of crisis |  | done, and included in the draft ERP plan | The NIWG
3.Mapping existing capacities
3.1.Coordination
MPAs
311 | To map existing national mechanisms already in place guiding emergency response planning in country and humanitarian structures in place for coordination, to identify existing coordination structures to liaise with at subnational level |  | ongoing with the subnational level in risk prone provinces, to be finalized by end of Feb | The ERP task force
312 | To evaluate whether a specific Nutrition ERP task force needs to be established or which existing TWG can be used |  | Done, Task Force established | The Nutrition cluster SAG
313 | To evaluate whether an intersectoral working group can be established |  | ongoing discussions to be concluded by end of Jan 2023 | The NCC in consultation with other clusters
3.2.Information management
MPAs
321 | To review existing mechanisms and tools used for IM |  | by end of Jan 2023 | The IM Specialists at national and subnational levels
322 | Data disagreagted by age and sex are available as well as data for people with disability |  | by end of Jan 2023 | The IM Specialist and NCC
3.3.Needs assessments
MPAs
331 | To review existing methodologies for rapid nutrition assessments (for needs evaluation, for rapid MUAC screening, for Rapid SMART survey, etc.) methodologies for rapid nutrition assessments (for needs evaluation, for rapid MUAC screening, for Rapid SMART survey, etc.) |  | Done | The NIWG
332 | Nutrition-related questions are included in the rapid needs assessment methodology |  | by end of Jan 2023 | The NIWG jointly with the OCHA Assessment WG
3.4.Response provision
MPAs
341 | To map Nutrition partners and ongoing response, i.e., have Nutrition Cluster 4W matrix up-to-date and available (at national and sub-national level where risk-prone) |  | updated on a monthly basis, or weekly basis in intial phase of emergencies | The IM Specialists at national and subnational levels
342 | To have a tool for supply mapping, to list key Nutrition supplies in stock or to ensure any existing nutrition supplies stock mapping is up-to-date. |  | by end of Jan 2023 | The NCC and IM Specialists at national and subnational levels
343 | Each TWG (NIWG, Wasting WG, IYCF-E TWG) maintains a list of protocols and guidelines and ensure these protocols are up-to-date and validated/endorsed by Government |  | Done and listed in the ERP plan | TWGs
344 | Guidelines for mobile a health and nutrition units are up-to-date and in used |  | by end of Jan 2023 | The CMAM TWG jointly with the Health Cluster and MoH
345 | To review the community engagement strategy and communication tools |  | Done
346 | List of trained personnel on NiE is up-to-date and available |  | Done and listed in the ERP plan | TWGs
3.5. Funding
MPAs
351 | The Nutrition cluster/sector has defined a costing methodology for the nutrition response plan and if a nutrition response is already ongoing current funding requirements and gaps are up-to-date |  | Done and included in ERP plan | The NCC and SAG
4.Response analysis and early response planning
4.1.Pre-crisis assessments
411 | MPAs
412 | To review and to summarize results from any existing safety audits assessments, Gender dynamics assessment and any Protection risks relative to Nutrition that might have been already identified and will have to be taken into account for the response design |  | done, and included in the draft ERP plan | The ERP task force
413 | To analyse barriers faced by people with disability in accessing Nutrition services |  | by end of March 2023 | A Nutrition Partner agrees to take the lead and consult with the Protection cluster
414 | To consult with the Cash Working group and map capacities of Nutrition partners to use Cash and vouchers as a response modality |  | by end of March 2023 | A Nutrition Partner agrees to take the lead and consult with the Multipurpose Cash WG
4.2.Response design
MPAs
421 | The Nutrition cluster/sector has defined a response strategy including the definition of nutrition response packages tailored to the type of crisis (population displaced in sites vs in host communities, population in remote rural localions vs in urban areas, population on the move, etc.) |  | by end of Feb 2023 | The ERP Task Force
422 | Minimum package for intersectoral emergency response is designed jointly with other clusters (joint definition of indicators of prioritization and targeting, set of minimum integrated actions) |  | by end of March 2023 | The intersector WG
423 | Adolescent and maternal nutrition are part of the IYCF-E intervention package and includes the provision of micronutrient supplementation |  | by end of March 2023 | The IYCF TWG
424 | Ensure a strategy is in place to maintain support to the Family MUAC approach in affected areas; and identify more entry points for MUAC screening and referral |  | by end of March 2023 | The CMAM TWG
425 | Advocacy and communication strategies and tools are up-to-date (joint IFE statement; key messages on nutrition and health seeking behaviors, etc.) |  | by end of Feb 2023 | The ERP Task Force jointly with concerned TWGs
APAs
426 | To outline sets of prioritized Nutrition interventions to implement in the immediate (first weeks after onset), refine the early response actions |  | by end of Feb 2023 | The ERP Task Force
427 | To refine the forecasting of supply needs estimates, additional Human and financial resources required to deliver essential nutrition services thru mobile units and in cse of expended criteria approach |  | by end of March 2023 | The ERP Task Force jointly with Health cluster and MoH
5.Planning for operational arrangements
5.1.Coordination
MPAs
511 | Nutrition cluster/sector partners are familiar / have knowledge refreshed on humanitarian principles and standards, on AAP and PSEA, on the cluster approach |  | twice a year | in collaboration with OCHA | 2000
512 | Refresher training on Nutrition cluster coordination for local authorities and partners in risk prone area |  | By end of March 2023 | The NCC with support from the GNC Capacity building helpdesk | 1000
APAs
514 | To anticipate on roles and responsibilities for Nutrition cluster coordination arrangements in case activated at subnational level (in risk prone provinces) |  | to be finalized by end of Feb | The NCC in consultations with Provincial Health Department
5.2.Information management
MPAs
521 | Refresher training on the IM instruments in use for Nutrition for IM focal points of local authorities and partners in risk prone provinces |  | By end of March 2023 | The NC IM Specialist with support from OCHA IM
APAs
523 | To anticipate on any adjustements required in case of emergencies and implications on existing IM tools, and adjust IM mechanisms for data collection, monitoring and reporting and adjusting data flow and frequency, etc. |  | By end of March 2023 | The NC IM Specialist in consultations with MoH and partners
5.3.Needs assessments
MPAs
531 | Nutrition cluster / sectors partners are familiarized on the methodology in use for multi-sectoral rapid assessment of needs |  | by end of Feb 2023 | The NIWG jointly with the OCHA Assessment WG
532 | Nutrition cluster partners are trained on rapid MUAC assessments and SMART surveys |  | twice a year | The NIWG | 15000
533 | List of anthropometric equipment and other materials (including logistics means for data collection) are up-to-date |  | by end of Jan 2023 | The NIWG
APAs
534 | Staff in charge of Nutrition assessments in emergencies have been pre-identified and roles pre-agreed (for rapids needs assessments, MUAC screening, SMART surveys) |  | By end of Jan 2023 | The NIWG
5.4.Response provision
MPAs
541 | Local partners' capacities for core NiE competencies are strenghtened on a regular basis |  | on a regular basis | multiple actors supports MoH NiE capacity building plan | 20000
542 | Mechanisms for rapid response are agreed upon and deployable personnel trained accordingly |  | by end of Feb 2023 | the ERP task force in consultations with MoH | 10000
543 | The communication and community mobilization strategy is up-to-date and tools available in adequate languages |  | by end of Feb 2023 | the ERP task force in consultations with MoH | 2000
544 | Criteria for TSFP scale-up and blanket SFP are predefined and approved |  | by end of Jan 2023 | the ERP task force in consultations with MoH
APAs
545 | A detailled prepositioning strategy in place, additional supplies dispatched, alternative storage capacities mapped; alternative logisitics for transportation, redispatch, storage anticipated |  | by end of Feb 2023 | the ERP task force in conultations with Nutrition partners and Logistics Cluster
5.5. Funding and resources mobilization
MPAs
551 | Staffing needs for cluster coordination and IM are mapped and budgeted for, and included in the ERP plan ; funding for Nutrition cluster staff secured by CLA other partners organization and donors |  | by end of Jan 2023 | The ERP task force
552
APAs
553 | Nutrition personnel are familiar with simplified SOPs or accelerated procedures to be able to fast-track reprogramming, human resource mobilization, simplified financial and administrative procedures, partnership agreements |  | by end of Jan 2023 | The ERP task force
554 | To cost the ERP plan and its preparedness actions workplan |  | by end of Feb 2023 | the ERP task force and Nutrition cluster SAG
6. ERP plan document development
APAs
610 | The Nutrition multi-risk ERP plan is finalized |  | by end of Feb 2023 | The ERP task force and SAG
611 | The Preparedness actions workplan is implemented, monitored and updated on a regular basis |  | by end of Jan 2023 | The ERP task force
612 | The ERP plan is disseminated in risk-prone provinces and ERP events organized at district level |  | 2023-03-01 | The ERP task force and Nutrition sector at subnational level | 4000
613
54000