## Nutrition Cluster _2019
Somalia NUTRITION Cluster Strategic Operating Framework (Jan-Dec 2019)
Cluster Parners and project location | Refer to the next tab
Strategic Objective 1: Effective coordination of partner’s response to the needs of affected population and management of information on the nutrition situation and response. |  |  |  | Indicator: Maintain satisfactory and beyond level in CCPM on coordination
Output | Responsible Agencies | Supporting Agencies | Activities | Indicator | Target | Actual | Q1 | Q2 | Q3 | Q4 | Comment
1.1 Active forum of exchanges with cluster members | UNICEF/MoH/WFP/ NC | Cluster members | Regular cluster coordination meetings (monthly National & at field level and quarterly at NBO); Strategic meetings (SAG). | # of nutrition cluster meeting attended | 12 |  | 4 | 4 | 4 | 4 | National - Mogadishu
[5 empty] | 144 |  | 36 | 36 | 36 | 36 | Field Level
[5 empty] | 4 |  | 1 | 1 | 1 | 1 | Nairobi level - QRM
1.2 Operational communication platform for nutrition cluster | UNICEF | Cluster lead (UNICEF) | Maintain the nutrition cluster website page on a timely manner with updates from partners (programme performance, assesment findings, etc.). Issuance of a monthly nutrition cluster response plan update. | # of visits on the nutrition cluster page per month; # of downloads of the nutrition cluster response update. | 12 |  | 3 | 3 | 3 | 3 | Using ONA online platforms and humanitarianresponse.info
1.3 Nutrition Cluster adequately represented in other cluster forum (Inter-cluster,health, food security, WASH, Protection) | UNICEF / OCHA | Cluster members | Participate in other forum and promote collaborative work with other cluster partners. | # of meetings Nut cluster represented | 12 |  | 3 | 3 | 3 | 3
1.4 Partners proposal review process completed in a timely manner | OCHA | Cluster members | Review of partners proposal (SHF) | % of proposal reviewed | 60 |  | 15 | 15 | 15 | 15 | (Target is proportion of eligible partners with proposal approved by OCHA)
1.5 Regular monthly SAG and AIMWG meetings | MoH/ACF/Nutrition cluster | respective members | Review of strategic priorities and nutrition information/products (planning to implimentaion, M&E) | # of proposal reviewed | 12 |  | 3 | 3 | 3 | 3
1.6 Regular maintainance of ONA online platform for an integrated reporting and data management | UNICEF | respective members | ONA training, Dashboard genration and reports follow up/feed back | periodic summary dashboard made availble to partners | 12 |  | 3 | 3 | 3 | 3
Strategic Objective 2: Assessments, evaluation of nutrition situation and set-up of nutrition rapid response and surveilance |  |  |  | Indicators: # of rapid responses by Partners
Output | Responsible Agencies | Supporting Agencies | Activities | Indicator | Target | Actual | Q1 | Q2 | Q3 | Q4 | Comment
2.1 Partner with capacity and resource identified to establish a stand by team for Rapid Nutrition Response by district. | All cluster partners / NC | Nut cluster partners/MOH | Identify the lead partner in emergency nutrition response, Rationlization Plan III | # of response teams set up/ # of regions with lead agency identified | One primary/strategic partner in each districts | [5 empty] | Endorsed RP III
2.2 Rapid assessements conducted | All cluster partners/ Lead Partner | Nut cluster partners/MOH | Conduct / Participation in joint or stand alone rapid assessments in affected population | # assessments conducted | 12 |  | 4 | 4 | 4 | 4
2.3 SMART surveys conducted | All cluster partners | Nut cluster partners/MOH | Conduct SMART survey | # SMART survey results released five days of end of data collection | 8 |  | 2 | 2 | 2 | 2 | The SMART surveys doesn't include the seasonal FSNAU surveys
2.4 Early Warning Early Trigerring Mechnism effectively utilized | FSNAU/FAO | Nut cluster partners/MOH | Regular data update on facility admission and mass screening, use of analytical early warning indicators for response | # monthly updates | 12 |  | 3 | 3 | 3 | 3 | http://dashboard.fsnau.org
2.5 Somlai National Nutrition Survey and Assesments Guideline Developed | AIMWG/CLA | Nut cluster partners/MOH | Training and effective implimentaion of the guideline | % partners adhering to the new guideline | 100
Strategic Objective 3: Improved/scaled-up integrated management of acute malnutrition (improved coverage and quality of integrated severe and moderate acute malnutrition management) |  |  |  | Indicators: Number of beneficiaries admitted within OTP/SC; Number of beneficiaries admitted within SFP; Proportion of SAM and MAM management sites that meet SPHERE coverage and performance standards; Number of clients who are satisified with SAM/MAM services; Number of complaints on the quality of services
Output | Responsible Agencies | Supporting Agencies | Activities | Indicator | Target | Actual | Q1 | Q2 | Q3 | Q4 | Comment
3.1 RPIII - Integrated iMAM scale up plan developed | CLA/WFP/MOH | Nut cluster partners | Consolidation of existing services, gap identification and multiyear plan | Clear stratgey and guiding document for service scale up at all leves | 1 |  | X | X |  |  | This follows Rationalization Plan III which would be an output of Finalization of geotagging
3.1 Management of SAM among children under fives and other vulnerable groups as per national guidelines. | UNICEF | Nut cluster partners/MOH | Training and supervision of personel in charge of SAM Management, Mass screening of children, Management of SAM in pre-existing or newly established SC/OTPs Including referral | # of new SAM admissions, # of new SAM management facilities | 177534 |  | 44384 | 44384 | 44384 | 44384 | as per HRP target
3.2 Management of MAM among children under five (TSFP) | WFP | Nut cluster partners/MOH | Training and supervision of personel in charge of MAM Management, Mass screening of children, Management of MAM in pre-existing or newly established TSFP sites. | # of new admissions for MAM treatment, # of new TSFP sites | 470256 |  | 117564 | 117564 | 117564 | 117564 | as per HRP target
3.3 Management of MAM among pregnant and lactating women as per national guidelines. | WFP | Nut cluster partners/MOH | Training and supervision of personel in charge of MAM Management, Mass screening PLW, Management of MAM in pre-existing or newly established TSFP sites. | # of new PLW admissions for MAM management | 127501 |  | 31875 | 31875 | 31875 | 31875 | as per HRP target
3.4 Implimentation of Feedback mechnism with in Accountablity to Affected Populatiobn framework | Cluster | Nut cluster partners/MOH | Routine collection of feedback from beneficiaries on the quality of services | proportion of complaints/complement verified on the quality of services from the beneficiaries | 75% |  | 25% | 25% | 25% | 25%
Objective 4: Effective management of nutrition supply pipeline. |  |  |  | Indicator: # of stock out of essential commodities for the nutrition sector response.
Output | Responsible Agencies | Supporting Agencies |  | Indicator | Target | Actual | Q1 | Q2 | Q3 | Q4 | Comment
5.1 Sufficient stocks of "RUTF, other commodities for SAM treaatment, anthropometric kits, commodities for Mcts supplementation" available at country and end-user level | UNICEF | Nut cluster partners/MOH | Procurement and transportation, distribution of RUTF, other commodities for SAM, anthropometric kits, commodities for Mcts supplementation commodities to facilities | % of facilites with adequate supplies to manage SAM cases | <10% of facilities closed due to supply |  | 2.5% | 2.5% | 2.5% | 2.5% | We will Measure only essential supplies which would lead to the closure of facilities - RUTF and RUSF
5.2. Pre-positioning of SAM management and mcts supplementation supplies | UNICEF | Nut cluster partners/MOH | Procurement and pre-positioning set up of a contingency supply stocks (SAM/Mcts) | pre-positioning RUTF Qty in MT | 4000 |  | 1000 | 1000 | 1000 | 1000 | an entire RUTF requirement
5.3 Sufficient stock of RUSF at country and end-user level | WFP | Nut cluster partners/MOH | Procurement ,transportation and distribution of RUSF and other MAM management commodities | % of facilities that have supplies to manage cases | <10% of facilities closed due to supply |  | 2.5% | 2.5% | 2.5% | 2.5%
5.4. Pre-positioning of MAM management and RUSF supplies | WFP | Nut cluster partners/MOH | Procurement and set up of a contingency supply stocks (MAM/RUSF) | SFP/MAM supplies in MT | 25000 |  | 5000 | 5000 | 5000 | 5000 | an entire RUSF requirement
Objective 5: Capacity development, research and knowledge management |  |  |  | Indicator: # of stock out of essential commodities for the nutrition sector response.
Output | Responsible Agencies | Supporting Agencies |  | Indicator | Target | Actual | Q1 | Q2 | Q3 | Q4 | Comment
6.1 Training on integrated and comprehensive package of nutrition in emergency and prepardness | UNICEF | Nut cluster partners/MOH | Partners capcity mapped, training needs identified and ongoing capacity development implimented | # partners/trainess trained | 120 |  | 30 | 30 | 30 | 30 | Train TOTs-managers, ensure MoH represented; train only after the new guidelines and revisions are carried out.
6.2 Knowledge management need identification and continued response preparedness update | UNICEF | Nut cluster partners/MOH | KM and EPRP project | publications/documentaions | 2 |  |  | 1 |  | 1
NB: Responsible agencies mentioned based on current contribution and leadership accounatblity under each task. However it can be flexibly changed to any one of willing and capable partner to undertake/lead the task

## Implementation
KEY DEADLINES
2018 | [12 empty] | 2020
Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
MAIN ACTIVITIES
2019 Work Plan Approved
Donor Brief
Q1 Dashboard & QRM
RP III - Finalization
Brief SAG and Members
Donor Brief
Annual Dashboard
Annual Report
Brief SAG and Members
Q2 Dashbiard and QRM
Mid-Year HRP Progress Report
Brief SAG & Members
Q3 Dashboiard & QRM
Brief SAG and Members
Service Delivery
Service/Tool Review, Support & Development
QRM & 2018 Annual Revoiew - Nairobi

## New Estimates - Dec 2018
Livelihood Zone | Livelihood system | Categories | LZ population | Under 5 Population | GAM by WHZ + GAM by MUAC | SAM by WHZ + SAM by MUAC | MAM by WHZ + SAM by MUAC | Total Burden (Acutely malnourished) | Total Burden (Severely malnourished) | Total Burden (Moderately malnourished U5) (Annual) | Total Burden (Moderately malnourished U5) (Monthly) | MAM PLW % | Total PLW Burden (Annual) | Total PLW Burden (Monthly)
Northwest Agro-pastoral | Agro-Pastoral | Rural | 62026.1344 | 12405.2269 | 8.6% | 1.1% | 7.5% | 2773.8087 | 354.7895 | 2419.0192 | 883.1947 | 11.18% | 901.4878 | 300.4959
West Golis Pastoral | Pastoral | Rural | 55823.5209 | 11164.7042 | 9.7% | 1.1% | 8.6% | 2815.7384 | 319.3105 | 2496.4279 | 885.2912 | 12.61% | 915.115 | 305.0383
Guban Pastoral | Pastoral | Rural | 6202.6134 | 1240.5227 | 15.6% | 4.7% | 10.9% | 503.156 | 151.5919 | 351.5641 | 136.3264 | 20.28% | 163.5257 | 54.5086
Guban Pastoral | Pastoral | Rural | 4506.7019 | 901.3404 | 15.6% | 4.7% | 10.9% | 365.5837 | 110.1438 | 255.4399 | 99.0522 | 20.28% | 118.8147 | 39.6049
Northwest Agro-pastoral | Agro-Pastoral | Rural | 13520.1056 | 2704.0211 | 8.6% | 1.1% | 7.5% | 604.6191 | 77.335 | 527.2841 | 192.5138 | 11.18% | 196.5012 | 65.5004
West Golis Pastoral | Pastoral | Rural | 72107.2298 | 14421.446 | 9.7% | 1.1% | 8.6% | 3637.0887 | 412.4534 | 3224.6353 | 1143.5304 | 12.61% | 1182.0538 | 394.0179
Guban Pastoral | Pastoral | Rural | 79777.0613 | 15955.4123 | 15.6% | 4.7% | 10.9% | 6471.5152 | 1949.7514 | 4521.7638 | 1753.4094 | 20.28% | 2103.2424 | 701.0808
West Golis Pastoral | Pastoral | Rural | 4431.8417 | 886.3683 | 9.7% | 1.1% | 8.6% | 223.5421 | 25.3501 | 198.192 | 70.2835 | 12.61% | 72.6512 | 24.2171
Guban Pastoral | Pastoral | Rural | 66085.0362 | 13217.0072 | 15.6% | 4.7% | 10.9% | 5360.8181 | 1615.1183 | 3745.6999 | 1452.4742 | 20.28% | 1742.2659 | 580.7553
West Golis Pastoral | Pastoral | Rural | 2753.5432 | 550.7086 | 9.7% | 1.1% | 8.6% | 138.8887 | 15.7503 | 123.1385 | 43.6677 | 12.61% | 45.1388 | 15.0463
Northwest Agro-pastoral | Agro-Pastoral | Rural | 52432.4721 | 10486.4944 | 8.6% | 1.1% | 7.5% | 2344.7802 | 299.9137 | 2044.8664 | 746.5898 | 11.18% | 762.0535 | 254.0178
West Golis Pastoral | Pastoral | Rural | 62918.9665 | 12583.7933 | 9.7% | 1.1% | 8.6% | 3173.6327 | 359.8965 | 2813.7362 | 997.816 | 12.61% | 1031.4306 | 343.8102
NW Hawd Pastoral | Pastoral | Rural | 94378.4497 | 18875.6899 | 7.4% | 1.1% | 6.3% | 3631.6827 | 539.8447 | 3091.838 | 1228.7268 | 9.62% | 1180.2969 | 393.4323
Guban Pastoral | Pastoral | Rural | 38124.9174 | 7624.9835 | 15.6% | 4.7% | 10.9% | 3092.6933 | 931.773 | 2160.9203 | 837.9425 | 20.28% | 1005.1253 | 335.0418
West Golis Pastoral | Pastoral | Rural | 57187.3761 | 11437.4752 | 9.7% | 1.1% | 8.6% | 2884.5313 | 327.1118 | 2557.4195 | 906.9202 | 12.61% | 937.4727 | 312.4909
Northwest Agro-pastoral | Agro-Pastoral | Rural | 54801.257 | 10960.2514 | 8.6% | 1.1% | 7.5% | 2450.7122 | 313.4632 | 2137.249 | 780.3191 | 11.18% | 796.4815 | 265.4938
West Golis Pastoral | Pastoral | Rural | 10962.882 | 2192.5764 | 9.7% | 1.1% | 8.6% | 552.9678 | 62.7077 | 490.2601 | 173.8576 | 12.61% | 179.7145 | 59.9048
NW Hawd Pastoral | Pastoral | Rural | 43874.024 | 8774.8048 | 7.4% | 1.1% | 6.3% | 1688.2724 | 250.9594 | 1437.313 | 571.2023 | 9.62% | 548.6885 | 182.8962
Togdheer Agro-pastoral | Agro-Pastoral | Rural | 3133.8589 | 626.7718 | 9.637% | 1.422% | 8.215% | 157.0395 | 23.1698 | 133.8697 | 44.6232 | 12.53% | 51.0378 | 17.0126
West Golis Pastoral | Pastoral | Rural | 3133.8589 | 626.7718 | 9.7% | 1.1% | 8.6% | 158.0718 | 17.9257 | 140.1462 | 49.6991 | 12.61% | 51.3733 | 17.1244
NW Hawd Pastoral | Pastoral | Rural | 28901.8561 | 5780.3712 | 7.4% | 1.1% | 6.3% | 1112.1434 | 165.3186 | 946.8248 | 376.2775 | 9.62% | 361.4466 | 120.4822
NW Hawd Pastoral | Pastoral | Rural | 55136.0592 | 11027.2118 | 7.4% | 1.1% | 6.3% | 2121.6356 | 315.3783 | 1806.2573 | 717.8244 | 9.62% | 689.5316 | 229.8439
West Golis Pastoral | Pastoral | Rural | 5379.1277 | 1075.8255 | 9.7% | 1.1% | 8.6% | 271.3232 | 30.7686 | 240.5546 | 85.3062 | 12.61% | 88.18 | 29.3933
Togdheer Agro-pastoral | Agro-Pastoral | Rural | 6723.9097 | 1344.7819 | 9.637% | 1.422% | 8.215% | 336.939 | 49.7123 | 287.2267 | 95.7422 | 12.53% | 109.5052 | 36.5017
West Golis Pastoral | Pastoral | Rural | 30326.3717 | 6065.2743 | 9.7% | 1.1% | 8.6% | 1529.6622 | 173.4668 | 1356.1953 | 480.9383 | 12.61% | 497.1402 | 165.7134
Togdheer Agro-pastoral | Agro-Pastoral | Rural | 4737.0711 | 947.4142 | 9.637% | 1.422% | 8.215% | 237.3774 | 35.0229 | 202.3545 | 67.4515 | 12.53% | 77.1477 | 25.7159
NW Hawd Pastoral | Pastoral | Rural | 11198.6938 | 2239.7388 | 7.4% | 1.1% | 6.3% | 430.9257 | 64.0565 | 366.8692 | 145.7974 | 9.62% | 140.0509 | 46.6836
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 11198.6938 | 2239.7388 | 8.7% | 1.7% | 7% | 506.6289 | 98.9965 | 407.6325 | 174.3155 | 11.31% | 164.6544 | 54.8848
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 10038.7831 | 2007.7566 | 8.7% | 1.7% | 7% | 454.1545 | 88.7428 | 365.4117 | 156.2607 | 11.31% | 147.6002 | 49.2001
West Golis Pastoral | Pastoral | Rural | 334.6261 | 66.9252 | 9.7% | 1.1% | 8.6% | 16.8785 | 1.9141 | 14.9645 | 5.3068 | 12.61% | 5.4855 | 1.8285
NW Hawd Pastoral | Pastoral | Rural | 780.7942 | 156.1588 | 7.4% | 1.1% | 6.3% | 30.045 | 4.4661 | 25.5788 | 10.1653 | 9.62% | 9.7646 | 3.2549
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 17547.3522 | 3509.4704 | 8.7% | 1.7% | 7% | 793.8422 | 155.1186 | 638.7236 | 273.1369 | 11.31% | 257.9987 | 85.9996
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 7913.4314 | 1582.6863 | 8.7% | 1.7% | 7% | 358.0036 | 69.9547 | 288.0489 | 123.1781 | 11.31% | 116.3512 | 38.7837
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 50269.7852 | 10053.957 | 11.7% | 2.1% | 9.6% | 3058.4137 | 548.9461 | 2509.4677 | 1286.3214 | 15.21% | 993.9845 | 331.3282
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 49099.1784 | 9819.8357 | 8.7% | 1.7% | 7% | 2221.2468 | 434.0367 | 1787.2101 | 764.2632 | 11.31% | 721.9052 | 240.6351
West Golis Pastoral | Pastoral | Rural | 9227.0586 | 1845.4117 | 9.7% | 1.1% | 8.6% | 465.4128 | 52.7788 | 412.6341 | 146.3296 | 12.61% | 151.2592 | 50.4197
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 30756.862 | 6151.3724 | 8.7% | 1.7% | 7% | 1391.4404 | 271.8907 | 1119.5498 | 478.7522 | 11.31% | 452.2181 | 150.7394
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 18454.1172 | 3690.8234 | 11.7% | 2.1% | 9.6% | 1122.7485 | 201.519 | 921.2295 | 472.2106 | 15.21% | 364.8933 | 121.6311
Guban Pastoral | Pastoral | Rural | 3075.6862 | 615.1372 | 15.6% | 4.7% | 10.9% | 249.4997 | 75.1698 | 174.3299 | 67.6001 | 20.28% | 81.0874 | 27.0291
NW Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 119951.3953 | 23990.2791 | 8.7% | 1.7% | 7% | 5426.6011 | 1060.3703 | 4366.2308 | 1867.1278 | 11.31% | 1763.6454 | 587.8818
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 38354.4527 | 7670.8905 | 11.7% | 2.1% | 9.6% | 2333.4849 | 418.8306 | 1914.6543 | 981.4276 | 15.21% | 758.3826 | 252.7942
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 17361.022 | 3472.2044 | 11.7% | 2.1% | 9.6% | 1056.2446 | 189.5824 | 866.6622 | 444.2401 | 15.21% | 343.2795 | 114.4265
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 3063.7098 | 612.742 | 15.5% | 2% | 13.5% | 246.935 | 31.8626 | 215.0724 | 111.892 | 20.15% | 80.2539 | 26.7513
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 1323.9369 | 264.7874 | 9.8% | 2.114% | 7.686% | 67.4678 | 14.5525 | 52.9153 | 21.6422 | 12.74% | 21.927 | 7.309
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 7502.3091 | 1500.4618 | 15.5% | 2% | 13.5% | 604.6861 | 78.024 | 526.6621 | 273.9974 | 20.15% | 196.523 | 65.5077
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 31569.2463 | 6313.8493 | 11.7% | 2.1% | 9.6% | 1920.6729 | 344.7362 | 1575.9368 | 807.8053 | 15.21% | 624.2187 | 208.0729
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 4349.1544 | 869.8309 | 9.8% | 2.114% | 7.686% | 221.6329 | 47.8053 | 173.8276 | 71.0951 | 12.74% | 72.0307 | 24.0102
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 19571.1946 | 3914.2389 | 15.5% | 2% | 13.5% | 1577.4383 | 203.5404 | 1373.8979 | 714.7741 | 20.15% | 512.6674 | 170.8891
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 19571.1946 | 3914.2389 | 11.7% | 2.1% | 9.6% | 1190.7115 | 213.7174 | 976.994 | 500.7948 | 15.21% | 386.9812 | 128.9937
East Golis (Frankincense, Goats and Fishing) | Pastoral | Rural | 32370.918 | 6474.1836 | 11.7% | 2.1% | 9.6% | 1969.4467 | 353.4904 | 1615.9562 | 828.3187 | 15.21% | 640.0702 | 213.3567
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 3596.7687 | 719.3537 | 15.5% | 2% | 13.5% | 289.8996 | 37.4064 | 252.4932 | 131.3602 | 20.15% | 94.2174 | 31.4058
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 17433.4431 | 3486.6886 | 15.5% | 2% | 13.5% | 1405.1355 | 181.3078 | 1223.8277 | 636.6997 | 20.15% | 456.669 | 152.223
NE Hawd Pastoral | Pastoral | Rural | 39430.8117 | 7886.1623 | 16.4% | 3.5% | 12.9% | 3362.6596 | 717.6408 | 2645.0188 | 1252.0931 | 21.32% | 1092.8644 | 364.2881
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 80056.4965 | 16011.2993 | 15.5% | 2% | 13.5% | 6452.5536 | 832.5876 | 5619.9661 | 2923.8025 | 20.15% | 2097.0799 | 699.0266
NE Hawd Pastoral | Pastoral | Rural | 29319.2158 | 5863.8432 | 16.4% | 3.5% | 12.9% | 2500.3427 | 533.6097 | 1966.733 | 931.0077 | 21.32% | 812.6114 | 270.8705
Addun pastoral | Pastoral | Rural | 10547.5923 | 2109.5185 | 11.2% | 1.5% | 9.7% | 614.2918 | 82.2712 | 532.0206 | 237.2699 | 14.56% | 199.6448 | 66.5483
NE Northern Inland Pastoral (Goats ands Sheep) | Pastoral | Rural | 21094.3064 | 4218.8613 | 15.5% | 2% | 13.5% | 1700.2011 | 219.3808 | 1480.8203 | 770.4008 | 20.15% | 552.5654 | 184.1885
NE Hawd Pastoral | Pastoral | Rural | 14059.2382 | 2811.8476 | 16.4% | 3.5% | 12.9% | 1198.9718 | 255.8781 | 943.0937 | 446.4396 | 21.32% | 389.6658 | 129.8886
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 17570.8841 | 3514.1768 | 9.8% | 2.114% | 7.686% | 895.4123 | 193.1369 | 702.2754 | 287.2292 | 12.74% | 291.009 | 97.003
Addun pastoral | Pastoral | Rural | 14136.9945 | 2827.3989 | 11.2% | 1.5% | 9.7% | 823.3386 | 110.2686 | 713.07 | 318.0141 | 14.56% | 267.585 | 89.195
Addun pastoral | Pastoral | Rural | 14136.9945 | 2827.3989 | 11.2% | 1.5% | 9.7% | 823.3386 | 110.2686 | 713.07 | 318.0141 | 14.56% | 267.585 | 89.195
NE Hawd Pastoral | Pastoral | Rural | 17278.5489 | 3455.7098 | 16.4% | 3.5% | 12.9% | 1473.5146 | 314.4696 | 1159.0451 | 548.6662 | 21.32% | 478.8923 | 159.6308
Central Hawd Pastoral | Pastoral | Rural | 17278.5489 | 3455.7098 | 22.4% | 4.084% | 18.32% | 2012.9409 | 366.9423 | 1645.9985 | 548.6662 | 29.12% | 654.2058 | 218.0686
NE Hawd Pastoral | Pastoral | Rural | 32903.6503 | 6580.7301 | 16.4% | 3.5% | 12.9% | 2806.0233 | 598.8464 | 2207.1769 | 1044.8285 | 21.32% | 911.9576 | 303.9859
Cowpea Belt | Agro-Pastoral | Rural | 15589.9324 | 3117.9865 | 9.8% | 2.1% | 7.7% | 794.463 | 170.2421 | 624.2209 | 208.0736 | 12.74% | 258.2005 | 86.0668
Addun pastoral | Pastoral | Rural | 43651.8107 | 8730.3621 | 11.2% | 1.5% | 9.7% | 2542.2815 | 340.4841 | 2201.7973 | 981.955 | 14.56% | 826.2415 | 275.4138
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 18707.9189 | 3741.5838 | 9.8% | 2.1% | 7.7% | 953.3555 | 204.2905 | 749.0651 | 249.6884 | 12.74% | 309.8406 | 103.2802
Addun pastoral | Pastoral | Rural | 34367.4991 | 6873.4998 | 11.2% | 1.5% | 9.7% | 2001.5631 | 268.0665 | 1733.4967 | 773.1028 | 14.56% | 650.508 | 216.836
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 8012.8869 | 1602.5774 | 9.8% | 2.114% | 7.686% | 408.3367 | 88.0766 | 320.2601 | 130.9857 | 12.74% | 132.7094 | 44.2365
NE Hawd Pastoral | Pastoral | Rural | 7010.3238 | 1402.0648 | 16.4% | 3.5% | 12.9% | 597.8404 | 127.5879 | 470.2525 | 222.6071 | 21.32% | 194.2981 | 64.766
Cowpea Belt | Agro-Pastoral | Rural | 5562.6468 | 1112.5294 | 9.8% | 2.1% | 7.7% | 283.4725 | 60.7441 | 222.7284 | 74.2428 | 12.74% | 92.1286 | 30.7095
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 2331.5845 | 466.3169 | 9.8% | 2.1% | 7.7% | 118.8175 | 25.4609 | 93.3566 | 31.1189 | 12.74% | 38.6157 | 12.8719
Addun pastoral | Pastoral | Rural | 61562.4417 | 12312.4883 | 11.2% | 1.5% | 9.7% | 3585.3966 | 480.187 | 3105.2096 | 1384.8577 | 14.56% | 1165.2539 | 388.418
Central Hawd Pastoral | Pastoral | Rural | 3511.5999 | 702.32 | 22.4% | 4.084% | 18.32% | 409.0993 | 74.5754 | 334.5239 | 111.508 | 29.12% | 132.9573 | 44.3191
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 3905.0274 | 781.0055 | 14.3% | 2.6% | 11.7% | 290.3778 | 52.796 | 237.5819 | 79.194 | 18.59% | 94.3728 | 31.4576
Central Hawd Pastoral | Pastoral | Rural | 41120.8273 | 8224.1655 | 22.4% | 4.084% | 18.32% | 4790.5524 | 873.2778 | 3917.2746 | 1305.7582 | 29.12% | 1556.9295 | 518.9765
Central Hawd Pastoral | Pastoral | Rural | 26104.5301 | 5220.906 | 22.4% | 4.084% | 18.32% | 3041.1625 | 554.3786 | 2486.7839 | 828.928 | 29.12% | 988.3778 | 329.4593
Addun pastoral | Pastoral | Rural | 23555.8962 | 4711.1792 | 11.2% | 1.5% | 9.7% | 1371.8954 | 183.736 | 1188.1594 | 529.8939 | 14.56% | 445.866 | 148.622
Addun pastoral | Pastoral | Rural | 24802.4921 | 4960.4984 | 11.2% | 1.5% | 9.7% | 1444.4971 | 193.4594 | 1251.0377 | 557.9363 | 14.56% | 469.4616 | 156.4872
Cowpea Belt | Agro-Pastoral | Rural | 13227.9958 | 2645.5992 | 9.8% | 2.1% | 7.7% | 674.0987 | 144.4497 | 529.649 | 176.5497 | 12.74% | 219.0821 | 73.0274
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 2066.8743 | 413.3749 | 14.3% | 2.6% | 11.7% | 153.6928 | 27.9441 | 125.7486 | 41.9162 | 18.59% | 49.9502 | 16.6501
Central Hawd Pastoral | Pastoral | Rural | 1240.1246 | 248.0249 | 22.4% | 4.084% | 18.32% | 144.4738 | 26.3364 | 118.1374 | 39.3791 | 29.12% | 46.954 | 15.6513
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 17357.1832 | 3471.4366 | 9.8% | 2.1% | 7.7% | 884.5221 | 189.5404 | 694.9816 | 231.6605 | 12.74% | 287.4697 | 95.8232
Cowpea Belt | Agro-Pastoral | Rural | 33317.4741 | 6663.4948 | 9.8% | 2.1% | 7.7% | 1697.8585 | 363.8268 | 1334.0317 | 444.6772 | 12.74% | 551.804 | 183.9347
Beletweyne Southern Agro-Pastoral | Agro-Pastoral | Rural | 91068.7214 | 18213.7443 | 19.47% | 3.854% | 15.62% | 9221.4008 | 1825.0689 | 7396.3319 | 2465.444 | 25.31% | 2996.9552 | 998.9851
Hawd Pastoral (Hiran (Mataban)) | Pastoral | Rural | 34312.8471 | 6862.5694 | 16% | 3.5% | 12.5% | 2854.8289 | 624.4938 | 2230.3351 | 939.7145 | 20.8% | 927.8194 | 309.2731
Beletweyne Riverine Pump Irrigation | Riverine | Rural | 17888.6916 | 3577.7383 | 15.7% | 3.3% | 12.4% | 1460.4328 | 306.9699 | 1153.4628 | 484.2889 | 20.41% | 474.6407 | 158.2136
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 17888.6916 | 3577.7383 | 14.3% | 2.6% | 11.7% | 1330.2031 | 241.8551 | 1088.348 | 362.7827 | 18.59% | 432.316 | 144.1053
Southern Agro-Pastoral (Hiran (Jalalaqsi & Bulo-Burte)) | Agro-Pastoral | Rural | 50968.1833 | 10193.6367 | 15.7% | 3.3% | 12.4% | 4161.0425 | 874.614 | 3286.4285 | 1095.4762 | 20.41% | 1352.3388 | 450.7796
Southern Agro-Pastoral (Hiran (Jalalaqsi & Bulo-Burte)) | Riverine | Rural | 15291.4234 | 3058.2847 | 15.7% | 3.3% | 12.4% | 1248.3918 | 262.4008 | 985.991 | 328.6637 | 20.41% | 405.7273 | 135.2424
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 30582.8468 | 6116.5694 | 14.3% | 2.6% | 11.7% | 2274.1405 | 413.4801 | 1860.6604 | 620.2201 | 18.59% | 739.0957 | 246.3652
Southern Agro-Pastoral (Hiran (Jalalaqsi & Bulo-Burte)) | Agro-Pastoral | Rural | 41865.9366 | 8373.1873 | 15.7% | 3.3% | 12.4% | 3417.9351 | 718.4195 | 2699.5156 | 899.8385 | 20.41% | 1110.8289 | 370.2763
Southern Agro-Pastoral (Hiran (Jalalaqsi & Bulo-Burte)) | Riverine | Rural | 11011.6698 | 2202.334 | 15.7% | 3.3% | 12.4% | 898.9927 | 188.9603 | 710.0325 | 236.6775 | 20.41% | 292.1726 | 97.3909
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 55079.9403 | 11015.9881 | 14.3% | 2.6% | 11.7% | 4095.7444 | 744.6808 | 3351.0636 | 1117.0212 | 18.59% | 1331.1169 | 443.7056
Shabell Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 44911.2129 | 8982.2426 | 12.4% | 2.2% | 10.2% | 2895.875 | 513.7843 | 2382.0907 | 959.1752 | 16.12% | 941.1594 | 313.7198
Shabelle Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 2694.6728 | 538.9346 | 14.1% | 1.8% | 12.3% | 197.5734 | 25.2221 | 172.3513 | 57.4504 | 18.33% | 64.2114 | 21.4038
Shabelle Riverine Gravity Irrigation | Riverine | Rural | 35928.9704 | 7185.7941 | 14.5% | 2.9% | 11.6% | 2709.0444 | 541.8089 | 2167.2355 | 792.2148 | 18.85% | 880.4394 | 293.4798
Cowpea Belt | Agro-Pastoral | Rural | 6287.5698 | 1257.514 | 9.8% | 2.1% | 7.7% | 320.4146 | 68.6603 | 251.7543 | 83.9181 | 12.74% | 104.1347 | 34.7116
Cowpea Belt | Agro-Pastoral | Rural | 14410.8091 | 2882.1618 | 9.8% | 2.1% | 7.7% | 734.3748 | 157.366 | 577.0088 | 192.3363 | 12.74% | 238.6718 | 79.5573
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 15637.2609 | 3127.4522 | 9.8% | 2.1% | 7.7% | 796.8748 | 170.7589 | 626.1159 | 208.7053 | 12.74% | 258.9843 | 86.3281
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 613.2259 | 122.6452 | 14.3% | 2.6% | 11.7% | 45.5995 | 8.2908 | 37.3087 | 12.4362 | 18.59% | 14.8198 | 4.9399
Shabell Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 79241.6634 | 15848.3327 | 12.4% | 2.2% | 10.2% | 5109.5025 | 906.5246 | 4202.9778 | 1692.3755 | 16.12% | 1660.5883 | 553.5294
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 33017.3597 | 6603.4719 | 9.8% | 2.1% | 7.7% | 1682.5647 | 360.5496 | 1322.0151 | 440.6717 | 12.74% | 546.8335 | 182.2778
Shabelle Riverine Gravity Irrigation | Riverine | Rural | 33017.3597 | 6603.4719 | 14.5% | 2.9% | 11.6% | 2489.5089 | 497.9018 | 1991.6071 | 728.0153 | 18.85% | 809.0904 | 269.6968
Cowpea Belt | Agro-Pastoral | Rural | 19810.4158 | 3962.0832 | 9.8% | 2.1% | 7.7% | 1009.5388 | 216.3297 | 793.2091 | 264.403 | 12.74% | 328.1001 | 109.3667
Cowpea Belt | Agro-Pastoral | Rural | 27249.5729 | 5449.9146 | 9.8% | 2.1% | 7.7% | 1388.6382 | 297.5653 | 1091.0729 | 363.691 | 12.74% | 451.3074 | 150.4358
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 36332.7639 | 7266.5528 | 9.8% | 2.1% | 7.7% | 1851.5176 | 396.7538 | 1454.7639 | 484.9213 | 12.74% | 601.7432 | 200.5811
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 1297.5987 | 259.5197 | 14.3% | 2.6% | 11.7% | 96.4894 | 17.5435 | 78.9459 | 26.3153 | 18.59% | 31.3591 | 10.453
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 13559.2425 | 2711.8485 | 14.3% | 2.6% | 11.7% | 1008.2653 | 183.321 | 824.9443 | 274.9814 | 18.59% | 327.6862 | 109.2287
Shabelle Riverine Gravity Irrigation | Riverine | Rural | 94903.8589 | 18980.7718 | 14.5% | 2.9% | 11.6% | 7155.751 | 1431.1502 | 5724.6008 | 2092.5798 | 18.85% | 2325.6191 | 775.2064
Shabell Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 4065.1829 | 813.0366 | 12.4% | 2.2% | 10.2% | 262.123 | 46.5057 | 215.6173 | 86.8207 | 16.12% | 85.19 | 28.3967
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 2710.4196 | 542.0839 | 9.8% | 2.1% | 7.7% | 138.123 | 29.5978 | 108.5252 | 36.1751 | 12.74% | 44.89 | 14.9633
Shabelle Riverine Gravity Irrigation | Riverine | Rural | 30922.7118 | 6184.5424 | 14.5% | 2.9% | 11.6% | 2331.5725 | 466.3145 | 1865.258 | 681.8294 | 18.85% | 757.7611 | 252.587
Shabell Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 113383.2765 | 22676.6553 | 12.4% | 2.2% | 10.2% | 7310.9537 | 1297.1047 | 6013.849 | 2421.5428 | 16.12% | 2376.0599 | 792.02
Coastal Deeh Pastoral and Fishing | Pastoral | Rural | 2945.0202 | 589.004 | 9.8% | 2.1% | 7.7% | 150.0782 | 32.1596 | 117.9186 | 39.3062 | 12.74% | 48.7754 | 16.2585
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 41901.7196 | 8380.3439 | 14.3% | 2.6% | 11.7% | 3115.8119 | 566.5112 | 2549.3006 | 849.7669 | 18.59% | 1012.6389 | 337.5463
Riverine Gravity Irrigation | Riverine | Rural | 4656.31 | 931.262 | 18.3% | 2.6% | 15.7% | 443.0945 | 62.9533 | 380.1411 | 126.7137 | 23.79% | 144.0057 | 48.0019
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 33381.8769 | 6676.3754 | 14.3% | 2.6% | 11.7% | 2482.2764 | 451.323 | 2030.9534 | 676.9845 | 18.59% | 806.7398 | 268.9133
Riverine Gravity Irrigation | Riverine | Rural | 185121.9315 | 37024.3863 | 18.3% | 2.6% | 15.7% | 17616.203 | 2502.8485 | 15113.3545 | 5037.7848 | 23.79% | 5725.266 | 1908.422
Shabelle Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 25443.4913 | 5088.6983 | 14.1% | 1.8% | 12.3% | 1865.5168 | 238.1511 | 1627.3657 | 542.4552 | 18.33% | 606.293 | 202.0977
Riverine Gravity Irrigation | Riverine | Rural | 170143.4687 | 34028.6937 | 18.3% | 2.6% | 15.7% | 16190.8525 | 2300.3397 | 13890.5128 | 4630.1709 | 23.79% | 5262.0271 | 1754.009
Shabell Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 36425.1955 | 7285.0391 | 12.4% | 2.2% | 10.2% | 2348.6966 | 416.7042 | 1931.9924 | 777.9381 | 16.12% | 763.3264 | 254.4421
Shabelle Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 24700.1867 | 4940.0373 | 14.1% | 1.8% | 12.3% | 1811.0177 | 231.1937 | 1579.8239 | 526.608 | 18.33% | 588.5807 | 196.1936
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 504.2129 | 100.8426 | 14.3% | 2.6% | 11.7% | 37.4933 | 6.817 | 30.6763 | 10.2254 | 18.59% | 12.1853 | 4.0618
Riverine Gravity Irrigation | Riverine | Rural | 14233.5905 | 2846.7181 | 18.3% | 2.6% | 15.7% | 1354.4685 | 192.4381 | 1162.0303 | 387.3434 | 23.79% | 440.2023 | 146.7341
Shabelle Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 775.6645 | 155.1329 | 14.1% | 1.8% | 12.3% | 56.8717 | 7.2602 | 49.6115 | 16.5372 | 18.33% | 18.4833 | 6.1611
Shabell Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 43810.5627 | 8762.1125 | 12.4% | 2.2% | 10.2% | 2824.9051 | 501.1928 | 2323.7122 | 935.6684 | 16.12% | 918.0942 | 306.0314
Shabelle Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 10952.6407 | 2190.5281 | 14.1% | 1.8% | 12.3% | 803.0476 | 102.5167 | 700.5309 | 233.5103 | 18.33% | 260.9905 | 86.9968
Bay Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 125076.142 | 25015.2284 | 20.02% | 2.962% | 17.06% | 13021.2057 | 1926.607 | 11094.5987 | 3698.1996 | 26.03% | 4231.8919 | 1410.6306
Bay-Bakool Agro-pastoral Low Potential | Agro-Pastoral | Rural | 53604.0609 | 10720.8122 | 13.1% | 2.3% | 10.8% | 3651.5086 | 641.1046 | 3010.4041 | 1584.9427 | 17.03% | 1186.7403 | 395.5801
Bay-Bakool Agro-pastoral Low Potential | Agro-Pastoral | Rural | 49854.1225 | 9970.8245 | 13.1% | 2.3% | 10.8% | 3396.0628 | 596.2553 | 2799.8075 | 1474.0661 | 17.03% | 1103.7204 | 367.9068
Bay Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 49854.1225 | 9970.8245 | 20.02% | 2.962% | 17.06% | 5190.1248 | 767.9266 | 4422.1982 | 1474.0661 | 26.03% | 1686.7906 | 562.2635
Bay Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 11078.6939 | 2215.7388 | 13.06% | 0.8565% | 12.21% | 752.4972 | 49.3441 | 703.1531 | 234.3844 | 16.98% | 244.5616 | 81.5205
Bay Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 61358.8562 | 12271.7712 | 20.02% | 2.962% | 17.06% | 6387.8392 | 945.1395 | 5442.6998 | 1814.2333 | 26.03% | 2076.0478 | 692.0159
Bay-Bakool Agro-pastoral Low Potential | Agro-Pastoral | Rural | 40905.9041 | 8181.1808 | 13.1% | 2.3% | 10.8% | 2786.5102 | 489.2346 | 2297.2756 | 1209.4888 | 17.03% | 905.6158 | 301.8719
Bay Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 41676.8481 | 8335.3696 | 20.02% | 2.962% | 17.06% | 4338.8196 | 641.9682 | 3696.8514 | 1232.2838 | 26.03% | 1410.1164 | 470.0388
Bay-Bakool Agro-pastoral Low Potential | Agro-Pastoral | Rural | 22441.3797 | 4488.2759 | 13.1% | 2.3% | 10.8% | 1528.7068 | 268.3989 | 1260.3079 | 663.5374 | 17.03% | 496.8297 | 165.6099
Bay-Bakool Agro-pastoral Low Potential (Wajid, Hudur) | Agro-Pastoral | Rural | 39114.3223 | 7822.8645 | 13.1% | 2.3% | 10.8% | 2664.4676 | 467.8073 | 2196.6603 | 1156.5161 | 17.03% | 865.952 | 288.6507
Bakool Southern Agro-Pastoral | Agro-Pastoral | Rural | 39114.3223 | 7822.8645 | 13.1% | 2.3% | 10.8% | 2664.4676 | 467.8073 | 2196.6603 | 1156.5161 | 17.03% | 865.952 | 288.6507
Bakool Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 47901.6749 | 9580.335 | 10.1% | 0.6% | 9.5% | 2515.796 | 149.4532 | 2366.3427 | 1013.423 | 13.13% | 817.6337 | 272.5446
Bay-Bakool Agro-pastoral Low Potential | Agro-Pastoral | Rural | 21686.5316 | 4337.3063 | 13.1% | 2.3% | 10.8% | 1477.2865 | 259.3709 | 1217.9156 | 405.9719 | 17.03% | 480.1181 | 160.0394
Bakool Southern Agro-Pastoral | Agro-Pastoral | Rural | 21686.5316 | 4337.3063 | 13.1% | 2.3% | 10.8% | 1477.2865 | 259.3709 | 1217.9156 | 405.9719 | 17.03% | 480.1181 | 160.0394
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 1807.211 | 361.4422 | 14.3% | 2.6% | 11.7% | 134.3842 | 24.4335 | 109.9507 | 36.6502 | 18.59% | 43.6749 | 14.5583
Bakool Southern Agro-Pastoral | Agro-Pastoral | Rural | 51481.126 | 10296.2252 | 13.1% | 2.3% | 10.8% | 3506.8943 | 615.7143 | 2891.18 | 1522.1726 | 17.03% | 1139.7406 | 379.9135
Bay-Bakool Agro-pastoral Low Potential (Wajid, Hudur) | Agro-Pastoral | Rural | 34320.7507 | 6864.1501 | 13.1% | 2.3% | 10.8% | 2337.9295 | 410.4762 | 1927.4534 | 1014.7817 | 17.03% | 759.8271 | 253.2757
Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 4515.8882 | 903.1776 | 13.06% | 0.8565% | 12.21% | 306.7323 | 20.1136 | 286.6187 | 95.5396 | 16.98% | 99.688 | 33.2293
South Gedo Southern Agro-Pastoral | Agro-Pastoral | Rural | 5187.4062 | 1037.4812 | 10.71% | 1.749% | 8.962% | 288.9073 | 47.1685 | 241.7388 | 80.5796 | 13.92% | 93.8949 | 31.2983
South Gedo Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 20749.625 | 4149.925 | 8.217% | 1.532% | 6.685% | 886.6274 | 165.3034 | 721.324 | 240.4413 | 10.68% | 288.1539 | 96.0513
South Gedo Riverine Pump Irrigation | Riverine | Rural | 8645.6771 | 1729.1354 | 13.57% | 1.467% | 12.1% | 610.0593 | 65.9524 | 544.1069 | 181.369 | 17.64% | 198.2693 | 66.0898
South Gedo Southern Agro-Pastoral | Agro-Pastoral | Rural | 4954.4285 | 990.8857 | 10.71% | 1.749% | 8.962% | 275.9319 | 45.0501 | 230.8818 | 76.9606 | 13.92% | 89.6779 | 29.8926
Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 29726.5713 | 5945.3143 | 10.71% | 1.749% | 8.962% | 1655.5913 | 270.3006 | 1385.2907 | 461.7636 | 13.92% | 538.0672 | 179.3557
South Gedo Riverine Pump Irrigation | Riverine | Rural | 20718.5194 | 4143.7039 | 13.57% | 1.467% | 12.1% | 1461.9474 | 158.0484 | 1303.899 | 434.633 | 17.64% | 475.1329 | 158.3776
South Gedo Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 34680.9998 | 6936.2 | 8.217% | 1.532% | 6.685% | 1481.9124 | 276.2887 | 1205.6236 | 401.8745 | 10.68% | 481.6215 | 160.5405
North Gedo Southern Agro-Pastoral | Agro-Pastoral | Rural | 3806.6133 | 761.3227 | 13.1% | 2.3% | 10.8% | 259.3065 | 45.5271 | 213.7794 | 71.2598 | 17.03% | 84.2746 | 28.0915
North Gedo Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 26660.8016 | 5332.1603 | 17.07% | 2.093% | 14.98% | 2366.4145 | 290.2206 | 2076.1938 | 692.0646 | 22.19% | 769.0847 | 256.3616
South Gedo Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 25527.3172 | 5105.4634 | 8.217% | 1.532% | 6.685% | 1090.7773 | 203.3653 | 887.412 | 295.804 | 10.68% | 354.5026 | 118.1675
South Gedo Southern Agro-Pastoral | Agro-Pastoral | Rural | 257.8517 | 51.5703 | 10.71% | 1.749% | 8.962% | 14.3608 | 2.3446 | 12.0162 | 4.0054 | 13.92% | 4.6673 | 1.5558
North Gedo Southern Agro-Pastoral | Agro-Pastoral | Rural | 2856.3189 | 571.2638 | 13.1% | 2.3% | 10.8% | 194.5724 | 34.1616 | 160.4109 | 53.4703 | 17.03% | 63.236 | 21.0787
North Gedo Riverine Pump Irrigation | Riverine | Rural | 1904.8156 | 380.9631 | 20.8% | 2.439% | 18.36% | 206.059 | 24.1586 | 181.9003 | 60.6334 | 27.04% | 66.9692 | 22.3231
North Gedo Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 13328.2822 | 2665.6564 | 17.07% | 2.093% | 14.98% | 1183.0192 | 145.0873 | 1037.9319 | 345.9773 | 22.19% | 384.4812 | 128.1604
North Gedo Southern Agro-Pastoral | Agro-Pastoral | Rural | 5820.2237 | 1164.0447 | 13.1% | 2.3% | 10.8% | 396.4736 | 69.6099 | 326.8638 | 108.9546 | 17.03% | 128.8539 | 42.9513
North Gedo Riverine Pump Irrigation | Riverine | Rural | 4366.4775 | 873.2955 | 20.8% | 2.439% | 18.36% | 472.3564 | 55.3797 | 416.9767 | 138.9922 | 27.04% | 153.5158 | 51.1719
North Gedo Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 16006.9249 | 3201.385 | 17.07% | 2.093% | 14.98% | 1420.7757 | 174.2461 | 1246.5296 | 415.5099 | 22.19% | 461.7521 | 153.9174
Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 20117.4178 | 4023.4836 | 14.3% | 2.6% | 11.7% | 1495.9312 | 271.9875 | 1223.9437 | 407.9812 | 18.59% | 486.1776 | 162.0592
Juba Riverine Gravity Irrigation | Riverine | Rural | 40227.1921 | 8045.4384 | 18.3% | 2.5% | 15.8% | 3828.0196 | 522.9535 | 3305.0661 | 1101.6887 | 23.79% | 1244.1064 | 414.7021
Juba Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 4020.4262 | 804.0852 | 14.1% | 1.8% | 12.3% | 294.7776 | 37.6312 | 257.1465 | 85.7155 | 18.33% | 95.8027 | 31.9342
Juba Pastoral (Cattle and Goats) | Pastoral | Rural | 12068.922 | 2413.7844 | 14.3% | 2.6% | 11.7% | 897.445 | 163.1718 | 734.2732 | 244.7577 | 18.59% | 291.6696 | 97.2232
Juba Pastoral (Cattle and Goats) | Pastoral | Rural | 33262.7273 | 6652.5455 | 14.3% | 2.6% | 11.7% | 2473.4164 | 449.7121 | 2023.7043 | 674.5681 | 18.59% | 803.8603 | 267.9534
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 33248.0502 | 6649.61 | 14.3% | 2.6% | 11.7% | 2472.325 | 449.5136 | 2022.8114 | 674.2705 | 18.59% | 803.5056 | 267.8352
Juba Riverine Gravity Irrigation | Riverine | Rural | 59124.8055 | 11824.9611 | 18.3% | 2.5% | 15.8% | 5626.3165 | 768.6225 | 4857.694 | 1619.2313 | 23.79% | 1828.5529 | 609.5176
Juba Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 14770.671 | 2954.1342 | 14.1% | 1.8% | 12.3% | 1082.9856 | 138.2535 | 944.7321 | 314.9107 | 18.33% | 351.9703 | 117.3234
Sorghum High Potential Agropastoral | Agro-Pastoral | Rural | 17247.8041 | 3449.5608 | 14.3% | 2.6% | 11.7% | 1282.5467 | 233.1903 | 1049.3564 | 349.7855 | 18.59% | 416.8277 | 138.9426
Juba Southern Agro-Pastoral | Agro-Pastoral | Rural | 7392.1874 | 1478.4375 | 13.1% | 2.3% | 10.8% | 503.5558 | 88.4106 | 415.1452 | 138.3817 | 17.03% | 163.6556 | 54.5519
Juba Riverine Pump Irrigation | Riverine | Rural | 16426.6421 | 3285.3284 | 18.3% | 2.5% | 15.8% | 1563.1593 | 213.5463 | 1349.6129 | 449.871 | 23.79% | 508.0268 | 169.3423
Juba Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 10949.3608 | 2189.8722 | 14.1% | 1.8% | 12.3% | 802.8071 | 102.486 | 700.3211 | 233.4404 | 18.33% | 260.9123 | 86.9708
Juba Riverine Gravity Irrigation | Riverine | Rural | 3420.377 | 684.0754 | 18.3% | 2.5% | 15.8% | 325.4831 | 44.4649 | 281.0182 | 93.6727 | 23.79% | 105.782 | 35.2607
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 6843.3199 | 1368.664 | 14.3% | 2.6% | 11.7% | 508.8693 | 92.5217 | 416.3476 | 138.7825 | 18.59% | 165.3825 | 55.1275
Juba Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 10263.6968 | 2052.7394 | 14.1% | 1.8% | 12.3% | 752.5343 | 96.0682 | 656.466 | 218.822 | 18.33% | 244.5736 | 81.5245
Juba Pastoral (Cattle and Goats) | Pastoral | Rural | 5131.8484 | 1026.3697 | 7.761% | 0.7463% | 7.015% | 207.1122 | 19.9146 | 187.1976 | 62.3992 | 10.09% | 67.3115 | 22.4372
Juba Southern Agro-Pastoral | Agro-Pastoral | Rural | 23204.9298 | 4640.986 | 13.1% | 2.3% | 10.8% | 1580.7198 | 277.531 | 1303.1889 | 434.3963 | 17.03% | 513.7339 | 171.2446
Juba Riverine Gravity Irrigation | Riverine | Rural | 18558.654 | 3711.7308 | 18.3% | 2.5% | 15.8% | 1766.0415 | 241.2625 | 1524.779 | 508.2597 | 23.79% | 573.9635 | 191.3212
Juba Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 26907.8441 | 5381.5688 | 14.1% | 1.8% | 12.3% | 1972.8831 | 251.8574 | 1721.0257 | 573.6752 | 18.33% | 641.187 | 213.729
Juba Pastoral (Cattle and Goats) | Pastoral | Rural | 19493.199 | 3898.6398 | 7.761% | 0.7463% | 7.015% | 786.7106 | 75.6452 | 711.0653 | 237.0218 | 10.09% | 255.6809 | 85.227
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 12884.7414 | 2576.9483 | 14.3% | 2.6% | 11.7% | 958.1094 | 174.2017 | 783.9077 | 261.3026 | 18.59% | 311.3855 | 103.7952
Juba Southern Inland Pastoral (Camel, Goats, Sheep and Cattle) | Pastoral | Rural | 5405.7928 | 1081.1586 | 14.1% | 1.8% | 12.3% | 396.3527 | 50.5982 | 345.7545 | 115.2515 | 18.33% | 128.8146 | 42.9382
Juba Pastoral (Cattle and Goats) | Pastoral | Rural | 12884.7414 | 2576.9483 | 14.3% | 2.6% | 11.7% | 958.1094 | 174.2017 | 783.9077 | 261.3026 | 18.59% | 311.3855 | 103.7952
Southern Rainfed (Maize, Cattle and Goats) | Agro-Pastoral | Rural | 32115.4983 | 6423.0997 | 14.3% | 2.6% | 11.7% | 2388.1085 | 434.2015 | 1953.9069 | 651.3023 | 18.59% | 776.1352 | 258.7117
Juba Riverine Gravity Irrigation | Riverine | Rural | 24978.9289 | 4995.7858 | 18.3% | 2.5% | 15.8% | 2376.9949 | 324.7261 | 2052.2688 | 684.0896 | 23.79% | 772.5233 | 257.5078
Urban | Urban | Urban | 263707.3911 | 52741.4782 | 8.7% | 1.7% | 7% | 11930.1224 | 2331.1733 | 9598.949 | 3199.6497 | 11.31% | 3877.2898 | 1292.4299
Urban | Urban | Urban | 4128.1354 | 825.6271 | 8.7% | 1.7% | 7% | 186.7568 | 36.4927 | 150.2641 | 50.088 | 11.31% | 60.696 | 20.232
Urban | Urban | Urban | 6233.5526 | 1246.7105 | 8.7% | 1.7% | 7% | 282.0059 | 55.1046 | 226.9013 | 75.6338 | 11.31% | 91.6519 | 30.5506
Urban | Urban | Urban | 5961.1326 | 1192.2265 | 8.7% | 1.7% | 7% | 269.6816 | 52.6964 | 216.9852 | 72.3284 | 11.31% | 87.6465 | 29.2155
Urban | Urban | Urban | 650014.3021 | 130002.8604 | 8.7% | 1.7% | 7% | 29406.647 | 5746.1264 | 23660.5206 | 7886.8402 | 11.31% | 9557.1603 | 3185.7201
Urban | Urban | Urban | 69497.8232 | 13899.5646 | 8.7% | 1.7% | 7% | 3144.0815 | 614.3608 | 2529.7208 | 843.2403 | 11.31% | 1021.8265 | 340.6088
Urban | Urban | Urban | 34684.5539 | 6936.9108 | 8.7% | 1.7% | 7% | 1569.1292 | 306.6115 | 1262.5178 | 420.8393 | 11.31% | 509.967 | 169.989
Urban | Urban | Urban | 321825.0088 | 64365.0018 | 8.7% | 1.7% | 7% | 14559.3634 | 2844.9331 | 11714.4303 | 3904.8101 | 11.31% | 4731.7931 | 1577.2644
Urban | Urban | Urban | 42776.7669 | 8555.3534 | 8.7% | 1.7% | 7% | 1935.2209 | 378.1466 | 1557.0743 | 519.0248 | 11.31% | 628.9468 | 209.6489
Urban | Urban | Urban | 19512.69 | 3902.538 | 8.7% | 1.7% | 7% | 882.7541 | 172.4922 | 710.2619 | 236.754 | 11.31% | 286.8951 | 95.6317
Urban | Urban | Urban | 29902.3971 | 5980.4794 | 8.7% | 1.7% | 7% | 1352.7844 | 264.3372 | 1088.4473 | 362.8158 | 11.31% | 439.6549 | 146.5516
Urban | Urban | Urban | 22390.9483 | 4478.1897 | 8.7% | 1.7% | 7% | 1012.9665 | 197.936 | 815.0305 | 271.6768 | 11.31% | 329.2141 | 109.738
Urban | Urban | Urban | 5728.7202 | 1145.744 | 8.7% | 1.7% | 7% | 259.1673 | 50.6419 | 208.5254 | 69.5085 | 11.31% | 84.2294 | 28.0765
Urban | Urban | Urban | 3974.5704 | 794.9141 | 8.7% | 1.7% | 7% | 179.8096 | 35.1352 | 144.6744 | 48.2248 | 11.31% | 58.4381 | 19.4794
Urban | Urban | Urban | 3320.3864 | 664.0773 | 8.7% | 1.7% | 7% | 150.2143 | 29.3522 | 120.8621 | 40.2874 | 11.31% | 48.8196 | 16.2732
Urban | Urban | Urban | 70845.6124 | 14169.1225 | 8.7% | 1.7% | 7% | 3205.0555 | 626.2752 | 2578.7803 | 859.5934 | 11.31% | 1041.643 | 347.2143
Urban | Urban | Urban | 21675.9159 | 4335.1832 | 8.7% | 1.7% | 7% | 980.6184 | 191.6151 | 789.0033 | 263.0011 | 11.31% | 318.701 | 106.2337
Urban | Urban | Urban | 13800.5745 | 2760.1149 | 8.7% | 1.7% | 7% | 624.338 | 121.9971 | 502.3409 | 167.447 | 11.31% | 202.9098 | 67.6366
Urban | Urban | Urban | 26612.3616 | 5322.4723 | 8.7% | 1.7% | 7% | 1203.9432 | 235.2533 | 968.69 | 322.8967 | 11.31% | 391.2816 | 130.4272
Urban | Urban | Urban | 313359.9087 | 62671.9817 | 15.8% | 2.1% | 13.7% | 25745.6501 | 3421.8902 | 22323.7599 | 7441.2533 | 20.54% | 8367.3363 | 2789.1121
Urban | Urban | Urban | 3460.3392 | 692.0678 | 15.8% | 2.1% | 13.7% | 284.3015 | 37.7869 | 246.5146 | 82.1715 | 20.54% | 92.398 | 30.7993
Urban | Urban | Urban | 7308.7762 | 1461.7552 | 15.8% | 2.1% | 13.7% | 600.489 | 79.8118 | 520.6772 | 173.5591 | 20.54% | 195.1589 | 65.053
Urban | Urban | Urban | 2869.8593 | 573.9719 | 15.8% | 2.1% | 13.7% | 235.7876 | 31.3389 | 204.4488 | 68.1496 | 20.54% | 76.631 | 25.5437
Urban | Urban | Urban | 5390.5101 | 1078.102 | 15.8% | 2.1% | 13.7% | 442.8843 | 58.8644 | 384.0199 | 128.0066 | 20.54% | 143.9374 | 47.9791
Urban | Urban | Urban | 42044.7091 | 8408.9418 | 15.8% | 2.1% | 13.7% | 3454.3933 | 459.1282 | 2995.2651 | 998.4217 | 20.54% | 1122.6778 | 374.2259
Urban | Urban | Urban | 86456.5244 | 17291.3049 | 15.8% | 2.1% | 13.7% | 7103.268 | 944.1052 | 6159.1628 | 2053.0543 | 20.54% | 2308.5621 | 769.5207
Urban | Urban | Urban | 27081.8567 | 5416.3713 | 15.8% | 2.1% | 13.7% | 2225.0453 | 295.7339 | 1929.3115 | 643.1038 | 20.54% | 723.1397 | 241.0466
Urban | Urban | Urban | 7080.1956 | 1416.0391 | 15.8% | 2.1% | 13.7% | 581.7089 | 77.3157 | 504.3931 | 168.131 | 20.54% | 189.0554 | 63.0185
Urban | Urban | Urban | 235461.9357 | 47092.3871 | 15.8% | 2.1% | 13.7% | 19345.5526 | 2571.2443 | 16774.3083 | 5591.4361 | 20.54% | 6287.3046 | 2095.7682
Urban | Urban | Urban | 36325.2959 | 7265.0592 | 15.8% | 2.1% | 13.7% | 2984.4863 | 396.6722 | 2587.8141 | 862.6047 | 20.54% | 969.9581 | 323.3194
Urban | Urban | Urban | 12130.1816 | 2426.0363 | 14.3% | 2.6% | 11.7% | 902.0003 | 164.0001 | 738.0002 | 246.0001 | 18.59% | 293.1501 | 97.7167
Urban | Urban | Urban | 21773.9499 | 4354.79 | 15.8% | 2.1% | 13.7% | 1788.9477 | 237.7715 | 1551.1762 | 517.0587 | 20.54% | 581.408 | 193.8027
Urban | Urban | Urban | 26201.2966 | 5240.2593 | 14.3% | 2.6% | 11.7% | 1948.3284 | 354.2415 | 1594.0869 | 531.3623 | 18.59% | 633.2067 | 211.0689
Urban | Urban | Urban | 34153.6651 | 6830.733 | 14.3% | 2.6% | 11.7% | 2539.6665 | 461.7576 | 2077.909 | 692.6363 | 18.59% | 825.3916 | 275.1305
Urban | Urban | Urban | 43831.4357 | 8766.2871 | 14.3% | 2.6% | 11.7% | 3259.3056 | 592.601 | 2666.7045 | 888.9015 | 18.59% | 1059.2743 | 353.0914
Urban | Urban | Urban | 47399.2207 | 9479.8441 | 14.3% | 2.6% | 11.7% | 3524.606 | 640.8375 | 2883.7686 | 961.2562 | 18.59% | 1145.497 | 381.8323
Urban | Urban | Urban | 11947.4911 | 2389.4982 | 14.3% | 2.6% | 11.7% | 888.4154 | 161.5301 | 726.8854 | 242.2951 | 18.59% | 288.735 | 96.245
Urban | Urban | Urban | 36329.7207 | 7265.9441 | 14.3% | 2.6% | 11.7% | 2701.478 | 491.1778 | 2210.3002 | 736.7667 | 18.59% | 877.9804 | 292.6601
Belet Weyne Urban | Urban | Urban | 30051.9536 | 6010.3907 | 14.3% | 1.6% | 12.7% | 2234.6633 | 250.0323 | 1984.631 | 796.5661 | 18.59% | 726.2656 | 242.0885
Urban | Urban | Urban | 24465.6505 | 4893.1301 | 14.3% | 2.6% | 11.7% | 1819.2658 | 330.7756 | 1488.4902 | 496.1634 | 18.59% | 591.2614 | 197.0871
Urban | Urban | Urban | 22209.444 | 4441.8888 | 14.3% | 2.6% | 11.7% | 1651.4943 | 300.2717 | 1351.2226 | 450.4075 | 18.59% | 536.7356 | 178.9119
Urban | Urban | Urban | 63220.5099 | 12644.102 | 14.3% | 2.6% | 11.7% | 4701.0771 | 854.7413 | 3846.3358 | 1282.1119 | 18.59% | 1527.8501 | 509.2834
Urban | Urban | Urban | 7197.859 | 1439.5718 | 14.3% | 2.6% | 11.7% | 535.2328 | 97.3151 | 437.9177 | 145.9726 | 18.59% | 173.9507 | 57.9836
Urban | Urban | Urban | 25347.326 | 5069.4652 | 14.3% | 2.6% | 11.7% | 1884.8272 | 342.6958 | 1542.1313 | 514.0438 | 18.59% | 612.5688 | 204.1896
Urban | Urban | Urban | 18818.8489 | 3763.7698 | 14.3% | 2.6% | 11.7% | 1399.3696 | 254.4308 | 1144.9388 | 381.6463 | 18.59% | 454.7951 | 151.5984
Urban | Urban | Urban | 40678.5009 | 8135.7002 | 14.3% | 2.6% | 11.7% | 3024.8533 | 549.9733 | 2474.88 | 824.96 | 18.59% | 983.0773 | 327.6924
Urban | Urban | Urban | 59584.8104 | 11916.9621 | 14.3% | 2.6% | 11.7% | 4430.7265 | 805.5866 | 3625.1399 | 1208.38 | 18.59% | 1439.9861 | 479.9954
Urban | Urban | Urban | 11892.975 | 2378.595 | 14.3% | 2.6% | 11.7% | 884.3616 | 160.793 | 723.5686 | 241.1895 | 18.59% | 287.4175 | 95.8058
Urban | Urban | Urban | 8330.6924 | 1666.1385 | 14.3% | 2.6% | 11.7% | 619.4703 | 112.631 | 506.8393 | 168.9464 | 18.59% | 201.3278 | 67.1093
Urban | Urban | Urban | 41008.324 | 8201.6648 | 14.3% | 2.6% | 11.7% | 3049.379 | 554.4325 | 2494.9464 | 831.6488 | 18.59% | 991.0482 | 330.3494
Urban | Urban | Urban | 6439.7712 | 1287.9542 | 14.3% | 2.6% | 11.7% | 478.8614 | 87.0657 | 391.7957 | 130.5986 | 18.59% | 155.63 | 51.8767
Urban | Urban | Urban | 40745.2393 | 8149.0479 | 14.3% | 2.6% | 11.7% | 3029.816 | 550.8756 | 2478.9404 | 826.3135 | 18.59% | 984.6902 | 328.2301
Urban | Urban | Urban | 25288.5936 | 5057.7187 | 14.3% | 2.6% | 11.7% | 1880.4598 | 341.9018 | 1538.558 | 512.8527 | 18.59% | 611.1494 | 203.7165
Urban | Urban | Urban | 17417.7124 | 3483.5425 | 14.3% | 2.6% | 11.7% | 1295.1811 | 235.4875 | 1059.6936 | 353.2312 | 18.59% | 420.9339 | 140.3113
Urban | Urban | Urban | 16380.6146 | 3276.1229 | 14.3% | 2.6% | 11.7% | 1218.0625 | 221.4659 | 996.5966 | 332.1989 | 18.59% | 395.8703 | 131.9568
Urban | Urban | Urban | 5244.9494 | 1048.9899 | 14.3% | 2.6% | 11.7% | 390.0144 | 70.9117 | 319.1027 | 106.3676 | 18.59% | 126.7547 | 42.2516
Urban | Urban | Urban | 18594.068 | 3718.8136 | 14.3% | 2.6% | 11.7% | 1382.6549 | 251.3918 | 1131.2631 | 377.0877 | 18.59% | 449.3628 | 149.7876
Urban | Urban | Urban | 4302.5289 | 860.5058 | 14.3% | 2.6% | 11.7% | 319.9361 | 58.1702 | 261.7659 | 87.2553 | 18.59% | 103.9792 | 34.6597
Urban | Urban | Urban | 16646.4901 | 3329.298 | 14.3% | 2.6% | 11.7% | 1237.833 | 225.0605 | 1012.7725 | 337.5908 | 18.59% | 402.2957 | 134.0986
Urban | Urban | Urban | 18055.5543 | 3611.1109 | 14.3% | 2.6% | 11.7% | 1342.611 | 244.1111 | 1098.4999 | 366.1666 | 18.59% | 436.3486 | 145.4495
Urban | Urban | Urban | 12862.5611 | 2572.5122 | 14.3% | 2.6% | 11.7% | 956.46 | 173.9018 | 782.5582 | 260.8527 | 18.59% | 310.8495 | 103.6165
Urban | Urban | Urban | 21204.1645 | 4240.8329 | 14.3% | 2.6% | 11.7% | 1576.7417 | 286.6803 | 1290.0614 | 430.0205 | 18.59% | 512.441 | 170.8137
Urban | Urban | Urban | 18796.0126 | 3759.2025 | 14.3% | 2.6% | 11.7% | 1397.6715 | 254.1221 | 1143.5494 | 381.1831 | 18.59% | 454.2432 | 151.4144
Urban | Urban | Urban | 7056.1851 | 1411.237 | 14.3% | 2.6% | 11.7% | 524.6979 | 95.3996 | 429.2983 | 143.0994 | 18.59% | 170.5268 | 56.8423
Urban | Urban | Urban | 5277.8254 | 1055.5651 | 14.3% | 2.6% | 11.7% | 392.4591 | 71.3562 | 321.1029 | 107.0343 | 18.59% | 127.5492 | 42.5164
Urban | Urban | Urban | 11007.3975 | 2201.4795 | 14.3% | 2.6% | 11.7% | 818.5101 | 148.82 | 669.6901 | 223.23 | 18.59% | 266.0158 | 88.6719
Urban | Urban | Urban | 16798.7249 | 3359.745 | 14.3% | 2.6% | 11.7% | 1249.1532 | 227.1188 | 1022.0344 | 340.6781 | 18.59% | 405.9748 | 135.3249
Urban | Urban | Urban | 19957.5581 | 3991.5116 | 14.3% | 2.6% | 11.7% | 1484.044 | 269.8262 | 1214.2178 | 404.7393 | 18.59% | 482.3143 | 160.7714
Urban | Urban | Urban | 17309.1754 | 3461.8351 | 14.3% | 2.6% | 11.7% | 1287.1103 | 234.0201 | 1053.0902 | 351.0301 | 18.59% | 418.3108 | 139.4369
Kismaayo Urban | Urban | Urban | 82323.3722 | 16464.6744 | 11.4% | 3.5% | 7.9% | 4880.1295 | 1498.2854 | 3381.8441 | 1747.7231 | 14.82% | 1586.0421 | 528.6807
Urban | Urban | Urban | 24591.6683 | 4918.3337 | 14.3% | 2.6% | 11.7% | 1828.6365 | 332.4794 | 1496.1571 | 498.719 | 18.59% | 594.3068 | 198.1023
Urban | Urban | Urban | 8118.5098 | 1623.702 | 14.3% | 2.6% | 11.7% | 603.6924 | 109.7623 | 493.9301 | 164.6434 | 18.59% | 196.2 | 65.4
Urban | Urban | Urban | 7179.6105 | 1435.9221 | 14.3% | 2.6% | 11.7% | 533.8758 | 97.0683 | 436.8075 | 145.6025 | 18.59% | 173.5096 | 57.8365
Banadir Urban | Urban | Urban | 1153228 | 230645.6 | 13.6% | 2.6% | 11% | 81556.2842 | 15591.6426 | 65964.6416 | 25459.675 | 17.68% | 26505.7924 | 8835.2641
IDP_Urb | IDP_Urb | IDPs | 10000 | 2000 | 8.7% | 1.7% | 7% | 452.4 | 88.4 | 364 | 121.3333 | 11.31% | 147.03 | 49.01
IDP_Urb | IDP_Urb | IDPs | 5000 | 1000 | 8.7% | 1.7% | 7% | 226.2 | 44.2 | 182 | 60.6667 | 11.31% | 73.515 | 24.505
IDP_Urb | IDP_Urb | IDPs | 9000 | 1800 | 8.7% | 1.7% | 7% | 407.16 | 79.56 | 327.6 | 109.2 | 11.31% | 132.327 | 44.109
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
Hargeysa IDP | IDP_Urb | IDPs | 99112.0079 | 19822.4016 | 9.8% | 1.8% | 8% | 5050.7479 | 927.6884 | 4123.0595 | 1570.1616 | 12.74% | 1641.4931 | 547.1644
Berbera IDP | IDP_Urb | IDPs | 12108.9572 | 2421.7914 | 8.7% | 1.7% | 7% | 547.8092 | 107.0432 | 440.766 | 163.5948 | 11.31% | 178.038 | 59.346
IDP_Urb | IDP_Urb | IDPs | 3000 | 600 | 8.7% | 1.7% | 7% | 135.72 | 26.52 | 109.2 | 36.4 | 11.31% | 44.109 | 14.703
Burco IDP | IDP_Urb | IDPs | 64752.9355 | 12950.5871 | 6.3% | 0.5% | 5.8% | 2121.3062 | 168.3576 | 1952.9485 | 742.3644 | 8.19% | 689.4245 | 229.8082
IDP_Urb | IDP_Urb | IDPs | 17148.259 | 3429.6518 | 8.7% | 1.7% | 7% | 775.7872 | 151.5906 | 624.1966 | 208.0655 | 11.31% | 252.1309 | 84.0436
IDP_Urb | IDP_Urb | IDPs | 13000 | 2600 | 8.7% | 1.7% | 7% | 588.12 | 114.92 | 473.2 | 157.7333 | 11.31% | 191.139 | 63.713
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 86950.6186 | 17390.1237 | 8.7% | 1.7% | 7% | 3933.646 | 768.6435 | 3165.0025 | 1055.0008 | 11.31% | 1278.4349 | 426.145
IDP_Urb | IDP_Urb | IDPs | 16740 | 3348 | 8.7% | 1.7% | 7% | 757.3176 | 147.9816 | 609.336 | 203.112 | 11.31% | 246.1282 | 82.0427
IDP_Urb | IDP_Urb | IDPs | 17000 | 3400 | 8.7% | 1.7% | 7% | 769.08 | 150.28 | 618.8 | 206.2667 | 11.31% | 249.951 | 83.317
IDP_Urb | IDP_Urb | IDPs | 18000 | 3600 | 8.7% | 1.7% | 7% | 814.32 | 159.12 | 655.2 | 218.4 | 11.31% | 264.654 | 88.218
IDP_Urb | IDP_Urb | IDPs | 3350 | 670 | 8.7% | 1.7% | 7% | 151.554 | 29.614 | 121.94 | 40.6467 | 11.31% | 49.255 | 16.4184
IDP_Urb | IDP_Urb | IDPs | 1800 | 360 | 8.7% | 1.7% | 7% | 81.432 | 15.912 | 65.52 | 21.84 | 11.31% | 26.4654 | 8.8218
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
Bossaso IDP | IDP_Urb | IDPs | 139577.8097 | 27915.5619 | 17.1% | 3.3% | 13.8% | 12411.2588 | 2395.1552 | 10016.1036 | 4873.0144 | 22.23% | 4033.6591 | 1344.553
IDP_Urb | IDP_Urb | IDPs | 2000 | 400 | 15.8% | 2.1% | 13.7% | 164.32 | 21.84 | 142.48 | 47.4933 | 20.54% | 53.404 | 17.8013
IDP_Urb | IDP_Urb | IDPs | 11000 | 2200 | 15.8% | 2.1% | 13.7% | 903.76 | 120.12 | 783.64 | 261.2133 | 20.54% | 293.722 | 97.9073
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 15.8% | 2.1% | 13.7% | 0 | 0 | 0 | 0 | 20.54% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 15.8% | 2.1% | 13.7% | 0 | 0 | 0 | 0 | 20.54% | 0 | 0
Qardho IDP | IDP_Urb | IDPs | 17282.9763 | 3456.5953 | 20.7% | 1.6% | 19.1% | 1860.3396 | 143.7944 | 1716.5452 | 851.1637 | 26.91% | 604.6104 | 201.5368
Garoowe IDP | IDP_Urb | IDPs | 30844 | 6168.8 | 16.7% | 2.5% | 14.2% | 2678.493 | 400.972 | 2277.521 | 855.4069 | 21.71% | 870.5102 | 290.1701
IDP_Urb | IDP_Urb | IDPs | 5000 | 1000 | 15.8% | 2.1% | 13.7% | 410.8 | 54.6 | 356.2 | 118.7333 | 20.54% | 133.51 | 44.5033
IDP_Urb | IDP_Urb | IDPs | 7800 | 1560 | 15.8% | 2.1% | 13.7% | 640.848 | 85.176 | 555.672 | 185.224 | 20.54% | 208.2756 | 69.4252
Gaalkacyo IDP | IDP_Urb | IDPs | 104835.2536 | 20967.0507 | 16.6% | 3.4% | 13.2% | 9049.3791 | 1853.4873 | 7195.8918 | 3234.4721 | 21.58% | 2941.0482 | 980.3494
IDP_Urb | IDP_Urb | IDPs | 3453.4099 | 690.682 | 15.8% | 2.1% | 13.7% | 283.7322 | 37.7112 | 246.0209 | 82.007 | 20.54% | 92.213 | 30.7377
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 15.8% | 2.1% | 13.7% | 0 | 0 | 0 | 0 | 20.54% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
Dhuusamarreeb IDP | IDP_Urb | IDPs | 30708 | 6141.6 | 14% | 1.6% | 12.4% | 2235.5424 | 255.4906 | 1980.0518 | 674.0562 | 18.2% | 726.5513 | 242.1838
IDP_Urb | IDP_Urb | IDPs | 64000 | 12800 | 14.3% | 2.6% | 11.7% | 4759.04 | 865.28 | 3893.76 | 1297.92 | 18.59% | 1546.688 | 515.5627
IDP_Urb | IDP_Urb | IDPs | 11000 | 2200 | 14.3% | 2.6% | 11.7% | 817.96 | 148.72 | 669.24 | 223.08 | 18.59% | 265.837 | 88.6123
IDP_Urb | IDP_Urb | IDPs | 22000 | 4400 | 14.3% | 2.6% | 11.7% | 1635.92 | 297.44 | 1338.48 | 446.16 | 18.59% | 531.674 | 177.2247
IDP_Urb | IDP_Urb | IDPs | 16000 | 3200 | 14.3% | 2.6% | 11.7% | 1189.76 | 216.32 | 973.44 | 324.48 | 18.59% | 386.672 | 128.8907
IDP_Urb | IDP_Urb | IDPs | 66000 | 13200 | 14.3% | 2.6% | 11.7% | 4907.76 | 892.32 | 4015.44 | 1338.48 | 18.59% | 1595.022 | 531.674
IDP_Urb | IDP_Urb | IDPs | 5000 | 1000 | 14.3% | 2.6% | 11.7% | 371.8 | 67.6 | 304.2 | 101.4 | 18.59% | 120.835 | 40.2783
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 26869.3297 | 5373.8659 | 14.3% | 2.6% | 11.7% | 1998.0034 | 363.2733 | 1634.73 | 544.91 | 18.59% | 649.3511 | 216.4504
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 12685 | 2537 | 14.3% | 2.6% | 11.7% | 943.2566 | 171.5012 | 771.7554 | 257.2518 | 18.59% | 306.5584 | 102.1861
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 42000 | 8400 | 14.3% | 2.6% | 11.7% | 3123.12 | 567.84 | 2555.28 | 851.76 | 18.59% | 1015.014 | 338.338
IDP_Urb | IDP_Urb | IDPs | 46030.645 | 9206.129 | 14.3% | 2.6% | 11.7% | 3422.8388 | 622.3343 | 2800.5044 | 933.5015 | 18.59% | 1112.4226 | 370.8075
IDP_Urb | IDP_Urb | IDPs | 13000 | 2600 | 14.3% | 2.6% | 11.7% | 966.68 | 175.76 | 790.92 | 263.64 | 18.59% | 314.171 | 104.7237
IDP_Urb | IDP_Urb | IDPs | 5000 | 1000 | 14.3% | 2.6% | 11.7% | 371.8 | 67.6 | 304.2 | 101.4 | 18.59% | 120.835 | 40.2783
IDP_Urb | IDP_Urb | IDPs | 10000 | 2000 | 14.3% | 2.6% | 11.7% | 743.6 | 135.2 | 608.4 | 202.8 | 18.59% | 241.67 | 80.5567
IDP_Urb | IDP_Urb | IDPs | 3000 | 600 | 14.3% | 2.6% | 11.7% | 223.08 | 40.56 | 182.52 | 60.84 | 18.59% | 72.501 | 24.167
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
Baydhaba IDP | IDP_Urb | IDPs | 246000 | 49200 | 17.7% | 3.6% | 14.1% | 22641.84 | 4605.12 | 18036.72 | 8607.3302 | 23.01% | 7358.598 | 2452.866
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 23568 | 4713.6 | 14.3% | 2.6% | 11.7% | 1752.5165 | 318.6394 | 1433.8771 | 477.959 | 18.59% | 569.5679 | 189.856
IDP_Urb | IDP_Urb | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Urb | IDP_Urb | IDPs | 18532.3741 | 3706.4748 | 14.3% | 2.6% | 11.7% | 1378.0673 | 250.5577 | 1127.5096 | 375.8365 | 18.59% | 447.8719 | 149.2906
IDP_Urb | IDP_Urb | IDPs | 9667 | 1933.4 | 14.3% | 2.6% | 11.7% | 718.8381 | 130.6978 | 588.1403 | 196.0468 | 18.59% | 233.6224 | 77.8741
IDP_Urb | IDP_Urb | IDPs | 1000 | 200 | 14.3% | 2.6% | 11.7% | 74.36 | 13.52 | 60.84 | 20.28 | 18.59% | 24.167 | 8.0557
IDP_Urb | IDP_Urb | IDPs | 13975 | 2795 | 14.3% | 2.6% | 11.7% | 1039.181 | 188.942 | 850.239 | 283.413 | 18.59% | 337.7338 | 112.5779
IDP_Urb | IDP_Urb | IDPs | 103000 | 20600 | 14.3% | 2.6% | 11.7% | 7659.08 | 1392.56 | 6266.52 | 2088.84 | 18.59% | 2489.201 | 829.7337
IDP_Urb | IDP_Urb | IDPs | 10363.1841 | 2072.6368 | 14.3% | 2.6% | 11.7% | 770.6064 | 140.1102 | 630.4961 | 210.1654 | 18.59% | 250.4471 | 83.4824
IDP_Urb | IDP_Urb | IDPs | 31000 | 6200 | 14.3% | 2.6% | 11.7% | 2305.16 | 419.12 | 1886.04 | 628.68 | 18.59% | 749.177 | 249.7257
IDP_Urb | IDP_Urb | IDPs | 4026 | 805.2 | 14.3% | 2.6% | 11.7% | 299.3734 | 54.4315 | 244.9418 | 81.6473 | 18.59% | 97.2963 | 32.4321
Doolow IDP | IDP_Urb | IDPs | 47000 | 9400 | 18.3% | 2.8% | 15.5% | 4472.52 | 684.32 | 3788.2 | 1520.1914 | 23.79% | 1453.569 | 484.523
IDP_Urb | IDP_Urb | IDPs | 600 | 120 | 14.3% | 2.6% | 11.7% | 44.616 | 8.112 | 36.504 | 12.168 | 18.59% | 14.5002 | 4.8334
IDP_Urb | IDP_Urb | IDPs | 9000 | 1800 | 14.3% | 2.6% | 11.7% | 669.24 | 121.68 | 547.56 | 182.52 | 18.59% | 217.503 | 72.501
IDP_Urb | IDP_Urb | IDPs | 17000 | 3400 | 14.3% | 2.6% | 11.7% | 1264.12 | 229.84 | 1034.28 | 344.76 | 18.59% | 410.839 | 136.9463
IDP_Urb | IDP_Urb | IDPs | 14000 | 2800 | 14.3% | 2.6% | 11.7% | 1041.04 | 189.28 | 851.76 | 283.92 | 18.59% | 338.338 | 112.7793
Kismaayo IDP | IDP_Urb | IDPs | 87000 | 17400 | 14.4% | 2.6% | 11.8% | 6514.56 | 1176.24 | 5338.32 | 2545.6938 | 18.72% | 2117.232 | 705.744
Afmadow/Xagar IDP | IDP_Urb | IDPs | 15958.1539 | 3191.6308 | 18.1% | 3.763% | 14.34% | 1502.0112 | 312.2994 | 1189.7118 | 396.5706 | 23.53% | 488.1536 | 162.7179
IDP_Urb | IDP_Urb | IDPs | 2000 | 400 | 14.3% | 2.6% | 11.7% | 148.72 | 27.04 | 121.68 | 40.56 | 18.59% | 48.334 | 16.1113
IDP_Urb | IDP_Urb | IDPs | 8000 | 1600 | 14.3% | 2.6% | 11.7% | 594.88 | 108.16 | 486.72 | 162.24 | 18.59% | 193.336 | 64.4453
Banadir IDP | IDP_Urb | IDPs | 497000 | 99400 | 16.7% | 4.1% | 12.6% | 43159.48 | 10596.04 | 32563.44 | 13172.9126 | 21.71% | 14026.831 | 4675.6103
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 2000 | 400 | 8.7% | 1.7% | 7% | 90.48 | 17.68 | 72.8 | 24.2667 | 11.31% | 29.406 | 9.802
IDP_Rul | IDP_Rul | IDPs | 887.9921 | 177.5984 | 8.7% | 1.7% | 7% | 40.1728 | 7.8499 | 32.3229 | 10.7743 | 11.31% | 13.0561 | 4.352
IDP_Rul | IDP_Rul | IDPs | 1891.0428 | 378.2086 | 8.7% | 1.7% | 7% | 85.5508 | 16.7168 | 68.834 | 22.9447 | 11.31% | 27.804 | 9.268
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 4247.0645 | 849.4129 | 8.7% | 1.7% | 7% | 192.1372 | 37.5441 | 154.5931 | 51.531 | 11.31% | 62.4446 | 20.8149
IDP_Rul | IDP_Rul | IDPs | 25851.741 | 5170.3482 | 8.7% | 1.7% | 7% | 1169.5328 | 228.5294 | 941.0034 | 313.6678 | 11.31% | 380.0981 | 126.6994
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 1000 | 200 | 8.7% | 1.7% | 7% | 45.24 | 8.84 | 36.4 | 12.1333 | 11.31% | 14.703 | 4.901
IDP_Rul | IDP_Rul | IDPs | 89049.3814 | 17809.8763 | 8.7% | 1.7% | 7% | 4028.594 | 787.1965 | 3241.3975 | 1080.4658 | 11.31% | 1309.2931 | 436.431
IDP_Rul | IDP_Rul | IDPs | 5260 | 1052 | 8.7% | 1.7% | 7% | 237.9624 | 46.4984 | 191.464 | 63.8213 | 11.31% | 77.3378 | 25.7793
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 12650 | 2530 | 8.7% | 1.7% | 7% | 572.286 | 111.826 | 460.46 | 153.4867 | 11.31% | 185.9929 | 61.9976
IDP_Rul | IDP_Rul | IDPs | 34200 | 6840 | 8.7% | 1.7% | 7% | 1547.208 | 302.328 | 1244.88 | 414.96 | 11.31% | 502.8426 | 167.6142
IDP_Rul | IDP_Rul | IDPs | 40000 | 8000 | 8.7% | 1.7% | 7% | 1809.6 | 353.6 | 1456 | 485.3333 | 11.31% | 588.12 | 196.04
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 8.7% | 1.7% | 7% | 0 | 0 | 0 | 0 | 11.31% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 1422.1903 | 284.4381 | 15.8% | 2.1% | 13.7% | 116.8472 | 15.5303 | 101.3168 | 33.7723 | 20.54% | 37.9753 | 12.6584
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 15.8% | 2.1% | 13.7% | 0 | 0 | 0 | 0 | 20.54% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 15.8% | 2.1% | 13.7% | 0 | 0 | 0 | 0 | 20.54% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 14000 | 2800 | 15.8% | 2.1% | 13.7% | 1150.24 | 152.88 | 997.36 | 332.4533 | 20.54% | 373.828 | 124.6093
IDP_Rul | IDP_Rul | IDPs | 9000 | 1800 | 15.8% | 2.1% | 13.7% | 739.44 | 98.28 | 641.16 | 213.72 | 20.54% | 240.318 | 80.106
IDP_Rul | IDP_Rul | IDPs | 3717.0237 | 743.4047 | 15.8% | 2.1% | 13.7% | 305.3907 | 40.5899 | 264.8008 | 88.2669 | 20.54% | 99.252 | 33.084
IDP_Rul | IDP_Rul | IDPs | 2156 | 431.2 | 15.8% | 2.1% | 13.7% | 177.137 | 23.5435 | 153.5934 | 51.1978 | 20.54% | 57.5695 | 19.1898
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 15.8% | 2.1% | 13.7% | 0 | 0 | 0 | 0 | 20.54% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 14200 | 2840 | 15.8% | 2.1% | 13.7% | 1166.672 | 155.064 | 1011.608 | 337.2027 | 20.54% | 379.1684 | 126.3895
IDP_Rul | IDP_Rul | IDPs | 17164.7464 | 3432.9493 | 15.8% | 2.1% | 13.7% | 1410.2556 | 187.439 | 1222.8165 | 407.6055 | 20.54% | 458.3331 | 152.7777
IDP_Rul | IDP_Rul | IDPs | 23546.5901 | 4709.318 | 15.8% | 2.1% | 13.7% | 1934.5878 | 257.1288 | 1677.4591 | 559.153 | 20.54% | 628.741 | 209.5803
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 6000 | 1200 | 15.8% | 2.1% | 13.7% | 492.96 | 65.52 | 427.44 | 142.48 | 20.54% | 160.212 | 53.404
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 292 | 58.4 | 14.3% | 2.6% | 11.7% | 21.7131 | 3.9478 | 17.7653 | 5.9218 | 18.59% | 7.0568 | 2.3523
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 7000 | 1400 | 14.3% | 2.6% | 11.7% | 520.52 | 94.64 | 425.88 | 141.96 | 18.59% | 169.169 | 56.3897
IDP_Rul | IDP_Rul | IDPs | 3130.6703 | 626.1341 | 14.3% | 2.6% | 11.7% | 232.7966 | 42.3267 | 190.47 | 63.49 | 18.59% | 75.6589 | 25.2196
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 8315 | 1663 | 14.3% | 2.6% | 11.7% | 618.3034 | 112.4188 | 505.8846 | 168.6282 | 18.59% | 200.9486 | 66.9829
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 9969.355 | 1993.871 | 14.3% | 2.6% | 11.7% | 741.3212 | 134.7857 | 606.5356 | 202.1785 | 18.59% | 240.9294 | 80.3098
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 10000 | 2000 | 14.3% | 2.6% | 11.7% | 743.6 | 135.2 | 608.4 | 202.8 | 18.59% | 241.67 | 80.5567
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 2432 | 486.4 | 14.3% | 2.6% | 11.7% | 180.8435 | 32.8806 | 147.9629 | 49.321 | 18.59% | 58.7741 | 19.5914
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 4467.6259 | 893.5252 | 14.3% | 2.6% | 11.7% | 332.2127 | 60.4023 | 271.8104 | 90.6035 | 18.59% | 107.9691 | 35.9897
IDP_Rul | IDP_Rul | IDPs | 333 | 66.6 | 14.3% | 2.6% | 11.7% | 24.7619 | 4.5022 | 20.2597 | 6.7532 | 18.59% | 8.0476 | 2.6825
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 25 | 5 | 14.3% | 2.6% | 11.7% | 1.859 | 0.338 | 1.521 | 0.507 | 18.59% | 0.60417 | 0.20139
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 636.8159 | 127.3632 | 14.3% | 2.6% | 11.7% | 47.3536 | 8.6098 | 38.7439 | 12.9146 | 18.59% | 15.3899 | 5.13
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 5974 | 1194.8 | 14.3% | 2.6% | 11.7% | 444.2266 | 80.7685 | 363.4582 | 121.1527 | 18.59% | 144.3737 | 48.1246
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 4400 | 880 | 14.3% | 2.6% | 11.7% | 327.184 | 59.488 | 267.696 | 89.232 | 18.59% | 106.3348 | 35.4449
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 52041.8461 | 10408.3692 | 14.3% | 2.6% | 11.7% | 3869.8317 | 703.6058 | 3166.2259 | 1055.4086 | 18.59% | 1257.6953 | 419.2318
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
IDP_Rul | IDP_Rul | IDPs | 0 | 0 | 14.3% | 2.6% | 11.7% | 0 | 0 | 0 | 0 | 18.59% | 0 | 0
|  |  | 12327530.3966 | 2465506.0793 | 14% | 2.2% | 11.8% | 848187.1601 | 151565.6519 | 696621.5083 | 260137.6691 |  | 275660.827 | 91886.9423

## 2019 - NCC FPs
Region | District/Location | Organization/Ministry | Name | Title (chair or Co-chair) | Email | Phone
Lower/Middle Juba | Kimayo | CARE | Muhuba Abdi Gedi | Chair | Muhuba.gedi@care.org | 25261742674
|  | MOH -JL | Ahmed Aseyr Haji | Co-chair | ljrnomoh@gmail.com | 252618459226
| Baidoa | DMO | Abdirahman Issack Mohamed | Chair | baylowershabelle@gmail.com | 252612451196
Bay/Lower Shabelle |  |  |  |  | aimsudeys@gmail.com
dmosomalia@gmail.com
|  | MOH -SWS | Mohamed Nur Hassan | Co-chair | Mohamed.moh.iswa@gmail.com | 252615918179
|  | New ways | Abdullahi Ibrahim Mohamed | Co-chair | Abdullahi.ibrahim@new-ways.org | 252617771050
Middle Shabelle | Jowhar | ZAMZAM | Mahat Omar Abukar: | Chair | mahaddaacad114@gmail.com | 252615680449
|  | MOH -HSH | Ismail Mohamed Ulusow: | Co-chair | ulusow2@gmail.com | 252615995660
Galgadud | Adaado | TUOS | Osman Abdullahi Nur | Chair | towfiiqorg@hotmail.com/osmanjicib@gmail.com | 252615684840
|  | SCI | Sahra Abdi Mohamud | Co-chair | Salad.halane@savethechildren.org | 252615573030
Banadir | Mogadishu | Centre for Peace and Democracy (CPD) | Abdulwahab Ali Osman | Chair
[5 empty] | Abdiwahab.ali@cpd-africa.org | +252 615 876564
|  | Save the Children International (SCI) | Maimun Abdullahi Gure | Co-Chair
[5 empty] | Maimun.Gure@savethechildren.org | +252 615 176165
|  | Ministry of Health (MoH) | Dr. Mohamed Hussein Alasow | Co-Chair
[5 empty] | M.alasow10@gmail.com | +252 615 562618
N. Mudug | Galkaio North | Save the Children International (SCI) | Mohamoud jama Mohamoud | Chair | Jama.Mohamoud@savethechildren.org
+252 907752925
|  | Ministry of Health (MoH) | Abdinasir Ibrahim Ahmed | Co-Chair
[5 empty] | Cabdinaasir10@hotmail.com | +252 907791080
Bakool | Xudur | GREDO | Omar Husein Digale | Chair | digale114@gmail.com | +252615192672
|  | MARDO | Abdikarim Abdullahi Ibrahim | Co-Chair | mardosom@gmail.com | +252-61598441
|  | SRDA | Ahmed Mohamed Abdullahi | Chair | amabdullahi@srdaorganization.org, gedo.nutritioncluster@hotmail.com | -615361958
Gedo | Dolow | HIRDA | Adan Ismail Hassan | Co-Chair | hirdahealth@yahoo.com | -619395252
S. Mudug |  | IMC | Ahmed Ilyas Mohamud | Nutrition officer | ahmedmohamud@internationalmedicalcorps.org | 252616262447
Galkayo South
|  | SRRDO | Ismail Mohamed Ahmed | Project officer | SRRDO60@hotmail.com | 252612927418
Bari |  | WFP. | Mohamed Hassan | Chair | Mohamed.hassan@wfp.org | 252907727299
| Bosaso | MOH, | Said Mohamed | Co-chair | Waraabe5@gmail.com | 252907796833
|  | MDM | Ayanle Abdullahi | Co-chari | Nutrition.program.manager@mdmfsomalia.org | 252906791539
|  | SCI | Abdi khadar Ali | Secretry | Abdikhadar.Ali@savethechildren.org | +25290 7597060
Hiran |  | SCI | Abdullahi Aden Moallim | Chair | abdullahi.moallim@savethechildren.org | +252615557603
| Beletweyn | RI | Hassan Ibrahim Galbed | Co-chair | hassan.galbed@ri.org | +252 615502690
Nugaal |  | UNICEF | Mohamed Isse Mohamud | Chair | mimohamoud@unicef.org | 252907797825
| Garowe | UNICEF | Dayib Mohamed Ismail | Co-chair | dsismail@unicef.org | 252907780926
|  | MoH -PL | Warsame Said Mohamed | Co-chair | warsame111@gmail.com | 252907790075
Somaliland Sector Coordination |  | MoH | Dr Ahmed Jama | Chair | drahmedj3@gmail.com , | 252634300240
| Hargiesa | UNICEF | Mohamed S. Abdillahi | Co-chair | msabdillahi@unicef.org | 252634211135