## NC Workplan 2019(Mid-year Rev)
Yemen Nutrition Cluster Work Plan 2019
Cluster objective | Sub-cluster activities | Responsible & Lead | Indicator | Target | Total budget | UNICEF budget | WFP budget | WHO budget | other budget | Monitoring | Aden Hub | Hudeidah hub | Ibb Hub | Sadaa hub | Sanaa Hub | Q1 | Q2 | Q3 | Q4 | Progress | Status | Remark
Reduce the prevalence of acute malnutrition through systematic identification, referral and treatment of acutely malnourished boys, girls under five and PLWs | SAM treatment | MoPHP, UNICEF, WHO & Nutrition cluster partners | Number and % of functional HFs providing SAM services % and number of children aged 0-59 mo with SAM treated/admitted Cure rate | 90% 80% of the SAM caseload in all districts - 285,990 More than 75% |  |  | 0 | 0 | 0 | CMAM database,4W and HFs tracking | 90% 46,605 More than 75% | 90% 108,901 More than 75% | 90% 51,989 More than 75% | 90% 20,306 More than 75% | 90% 58,188 More than 75% | x | x | x | x | 157,978 Child/Cases | • On track, 85% of HFs have SAM treatment (3,711 OTPs out of of 4,342 functional HFs) • 44% of annual caseload and 55% of annual target (84% reporting rate) | UNICEF has revised the SAM target and increased it to 90%. Cluster target has been adjusted accordingly.
| MAM treatment in children | MoPHP, WFP & Nutrition cluster partners | Number of TSFPs operational Number and % of children aged 6-59 mo with MAM treated | 85% of functional HFs in the targeted 120 districts (same where SAM is provided) as well as maintaining the TSFPs in the 112 districts 70% of the case load in the 107 targeted IFFR districts 2018 -and 60 % in the rest of districts within 295 whole targeted districts 937,879 |  |  | 0 | 0 | 0 | CMAM database,4W and HFs tracking | 201328 | 297214 | 199548 | 45501 | 194288 | x | x | x | x | 259,584 Child/Cases | • On track in regard to the program coverage, 70% of HFs have MAM treatment (3,028 OTPs out of of 4,342 functional HFs). • Delayed in regard to the treatment, 18% of annual caseload and 28% of annual target (73% reporting rate) | Low reporting rate could be the reason for low coverage against caseload and target.
| Treatment of AM in PLW | MoPHP, WFP & Nutrition cluster partners | Number and % of PLW with AM treated | 60% of the case load in 295 targeted districts -639,210 |  |  | 0 | 0 | 0 | CMAM database,4W and HFs tracking | 91419 | 214332 | 116425 | 41844 | 175190 | x | x | x | x | 268,016 PLW cases | • On track in regard to the program coverage, 70% of HFs have MAM treatment (3,028 OTPs out of 4,342 functional HFs). • On track in regard to the treatment, 23% of annual caseload and 42% of annual target (74% reporting rate)
| Deploy & maintain functionality of MTs in the areas where the HFs are not functional and in the hard to reach 2nd and 3rd level of coverage villages, with special focus on IDPs & marginalized population. | WFP, UNICEF, WHO, MoPHP and Nutrition Cluster Ips | % of hard to reach areas in the 2nd and 3rd level of coverage reached with MTs services Number of functional mobile teams providing nutrtion services | 200 |  |  | 0 | 0 | 0 | MTs Tracking Matrix, MTs reposnse matrix, MoPHP information for the hard to reach areas | [5 empty] | x | x | x | x | 187 MTs | • On track. Total number of mobile teams operational is 187
| Support scale up of TFCs in the entire country | WHO/UNICEF/MoPHP, NC partners | number of TFCs established | 134 TFCs | [5 empty] | reports from UNICEF, WHO sub-national focal points through the sub-clusters | [9 empty] | 104 TFCs | • On track. Total number of operational TFCs is 104(increased from 83 in Dec 2018 to 104 in June 2019)
| Support running cost for the already established functional 83 TFCs/SCs and the new SCs that will be established during 2019 | MoPHP, WHO, UNICEF, & NC Partners | # of functional TFCs/SCs nationwide # of chidlren with SAM with complications treated | 134 TFCs 21,449 targeted child | [5 empty] | HFs tracking matrix, CMAM database | [5 empty] | x | x | x | x | 7,217 Child/Cases | • Delayed, 20% of annual caseload and 34% of annual target (81% reporting rate)
| Increased frequency of screening (MUAC mass screenings/ referral and regular at household level) | Nutrition Cluster, MoPHP, UNICEF, WHO and WFP and Nutrition Cluster Partners | Number of mass screening conducted per governorate per year | 1 mass screening campaign per year | [5 empty] | MoPHP database of screening campaign | 1 mass screening campaign per year | 1 mass screening campaign per year | 1 mass screening campaign per year | 1 mass screening campaign per year | 1 mass screening campaign per year |  | x |  | x | 63 districts (953,079 child screened) | • MUAC screening conducted in 63 districts (953,079 child screened)
| Provision of update on supply pipeline to Nutrition Cluster and wider humanitarian community | UNICEF, WHO & WFP | Supply pipeline update provided every quarter | Quarterly report on supplies pipeline to be provided by UNICEF & WFP and bi-annual report to be provided by WHO | 0 | 0 | 0 | 0 | 0 | NC supply tracker, Cluster meeting minutes | Quarterly report on supplies pipeline to be provided by UNICEF & WFP and bi-annual report to be provided by WHO | Quarterly report on supplies pipeline to be provided by UNICEF & WFP and bi-annual report to be provided by WHO | Quarterly report on supplies pipeline to be provided by UNICEF & WFP and bi-annual report to be provided by WHO | Quarterly report on supplies pipeline to be provided by UNICEF & WFP and bi-annual report to be provided by WHO | Quarterly report on supplies pipeline to be provided by UNICEF & WFP and bi-annual report to be provided by WHO | x | x | x | x | Supplies availability tracked at HF on monthly basis | • 96% of OTPs with no stock out of RUTF, 77% of TSFPs with no stock out of RUSF and 60% of WSB+(NGOs inputs) | Only for NGOs
| Procure and distribute essential supplies for the management of severe & moderate acute malnutrition including registers…etc. | UNICEF& WFP, WHO, MoPHP/GHOs | % of OTPs, TSFPs & TFCs with zero stock out | 0 stock out of supplies materials | 0 | 0 | 0 | 0 | 0 | Reports from UNICEF, WFP and WHO sub-national focal points through the sub-clusters | 0 stock out of supplies materials | 0 stock out of supplies materials | 0 stock out of supplies materials | 0 stock out of supplies materials | 0 stock out of supplies materials | x | x | x | x | 99% OTPs reported zero stock in 2018 as per TPM | 99% OTPs reported zero stock in 2018 as per TPM | the indicator has been changed to percentage OTP, TSFP with zero stock
| Identify and capacitated LNGOs that have potential to take on nutrition programming | UNICEF, WHO and WFP, Nutrition Clusters at national and sub-national levels | Number of new national LNGOs starting the implementation of nutrition interventions | 5 more LNGO to be identified/ capacitated | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | [5 empty] | x | x | x | x | 4 new LNGOs (IFMC, IYCY, YHO, RRD) | on track
| Strengthen M&E, supervision and reporting system by supporting regular monitoring visits to service delivery sites at all levels ( central, governorate, zonal & district level) | MoPHP, UNICEF, WHO, WFP & NGOs partners | Number of supervision visits conducted | Monthly supervision visits to be conducted by district level monitors, bi-quarterly or quarterly monitoring visits to be conducted by governorate level monitors & bi annual monitoring visits to be conducted by central level monitors |  |  | 0 | 0 | 0 | MoPHP | Monthly monitoring visits to be conducted by district level monitors, bi-quarterly or quarterly monitoring visits to be conducted by governorate level monitors & bi annual monitoring visits to be conducted by central level monitors | Monthly monitoring visits to be conducted by district level monitors, bi-quarterly or quarterly monitoring visits to be conducted by governorate level monitors & bi annual monitoring visits to be conducted by central level monitors | Monthly monitoring visits to be conducted by district level monitors, bi-quarterly or quarterly monitoring visits to be conducted by governorate level monitors & bi annual monitoring visits to be conducted by central level monitors | Monthly monitoring visits to be conducted by district level monitors, bi-quarterly or quarterly monitoring visits to be conducted by governorate level monitors & bi annual monitoring visits to be conducted by central level monitors | Monthly monitoring visits to be conducted by district level monitors, bi-quarterly or quarterly monitoring visits to be conducted by governorate level monitors & bi annual monitoring visits to be conducted by central level monitors | x | x | x | x | More than 3,900 supervision visit were supported
| Provide operational costs to non-supported health facilities to provide curative and preventive nutrition services | UNICEF/MoPHP | Number of health fcilities supported with operational costs | 80% of the non-supported health facilities supported | [5 empty] | UNICEF/MoPHP | [9 empty] | 2000 health facilities has been supported by UNICEF as part of WB project | 2000 health facilities has been supported by UNICEF as part of WB project
| Follow up CMAM timely reporting with partners to address bottlenecks identified | MoPHP, UNICEF and WFP in consultation with the Nutrition Cluster IMO / Nutrition Cluster partners | Reporting rate for CMAM activities on monthly basis | 80% | 0 | 0 | 0 | 0 | 0 | Reporting Rate in CMAM Monthly Compiler. | 80% | 80% | 80% | 80% | 80% | x | x | x | x | 84% OTPs reporting rate 81% TFCs reporting rate 73% TSFPs reporting rate | on track | Reports are submitted very late (3 weeks after the deadline on the 10th of subsequent month)
| Introduce harmonized agreed approach to performance based incentives/ Implement harmonized incentive rates and modalities of payment for all community and facility based cadres including CHVs, CHWs and FHWs. | MoPHP, UNICEF, WFP, WHO and Nutrition Cluster Partners | Nutrition cluster adopted MoPH harmonized agreed approach to performance based incentives | 1 harmonized support system to CHVs and HWs in place | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | 1 harmonized support system to CHVs and HWs in place | 1 harmonized support system to CHVs and HWs in place | 1 harmonized support system to CHVs and HWs in place | 1 harmonized support system to CHVs and HWs in place | 1 harmonized support system to CHVs and HWs in place | x |  |  |  | UNICEF to update
| Harmonize and align treatment protocal and referal mechanisms for SAM cases with suspected cholera/AWD with exisiting cholera treatment protocols. | MoPHP/UNICEF/WHO/ NCCT | Mechanisms for SAM cases with suspected cholera/AWD with exisiting cholera treatment protocol developed | [6 empty] | mechanisms for SAM cases l | [9 empty] | Bending the updates
| Provision of consumable hygiene WASH kits to all SAM children | WASH cluster/NCC | Number of SAM children provided with consumable WASH hygiene kits | All SAM cases | [5 empty] | Nutrition/WASH cluster monitoring data bases | [9 empty] | 38% of nutrition sites providing hygiene kits to SAM cases and 42 provided soap | not on track | Need to conduct a follow up assessment
| Provide basic WASH kits to SAM children | WASH cluster? | numbe of children with SAM provided with basic WASH kits | All SAM cases | [5 empty] | Nutrition/WASH cluster monitoring data bases | [9 empty] | 38% of nutrition sites providing hygiene kits to SAM cases and 42 provided soap | not on track | Assessment of WASH services availability in Nutrition sites has been done. Partners requested to submit the budget needed for providing the WASH services
| Strengthen community component, including CHWs and CHVs | MoPHP, partners | Number of CHVs active | Priority districts (165 districts): 40% of the needs. Other districts: 10% of the needs | 0 | 0 | 0 | 0 | 0 | Only those that report to the cluster considered active | Priority districts within165 districts 40% of the needs. Other districts: 10% of the needs | Priority districts within 165 districts 40% of the needs. Other districts: 10% of the needs | Priority districts within165 districts 40% of the needs. Other districts: 10% of the needs | Priority districts within165 districts 40% of the needs. Other districts: 10% of the needs | Priority districts within165 districts 40% of the needs. Other districts: 10% of the needs | x | x | x | x | 15,241 CHVs | • On track: 43% of total CHVs needed (35,716)
Strengthen humanitarian life-saving preventive nutrition services for vulnerable population groups focusing on appropriate IYCF practices in emergency, micro-nutrient, BSFP interventions and optimal maternal nutrition | Vitamin A supplementation | MoPHP, UNICEF & Nutrition cluster partners | number and % of children aged 6-59 mo received vitamin A supplementation at least once | 90% of children aged 6-59 mo -4,290,047 |  |  | 0 | 0 | 0 | CMAM database, CHVs database, outreach ,MTs weekly database, Campaigns' databases | 837495 | 987742 | 877548 | 226374 | 1360888 | x | x | x | x | 50,378 Child | • Delayed (1% of caseload), due to delay of implementing the national campaigns
| Micronutrient supplementation through MNPs of children aged 6-59 | MoPHP, UNICEF, Nutrition cluster partners | Number and % of children 6-59 month received micronutrient supplementation through MNPs | 60% of children aged 6-59 mo in all districts 2,860,032 |  |  | 0 | 0 | 0 | CMAM database, CHVs database, outreach MTs database weekly database, Campaigns' databases | 558330 | 658495 | 585032 | 150916 | 907259 | x | x | x | x | 971,767 Child | • Delayed, 20% of annual caseload and 34% of annual target, this year NC/UNICEF increased the targeted children from 6-23mo last year to 6-59 mo this year
| BSFP for children 6-23 month | MoPHP, WFP & Nutrition cluster partners | Number and % of children 6-23 month received BSFP | 100% of children aged 6-23 mo in 99 districts that have access out of 107 districts, and 60 % of targeted children in in the rest of 58 districts, 688,098 |  |  | 0 | 0 | 0 | BSFP database, WFP, NC Partners | 157394 | 233134 | 175591 | 20058 | 101921 | x | x | x | x | 298,392 Child | • On track: 37% of annual caseload and 43% of annual target
| Develop short guidelines on MNPs supplementation ways to scale it up in the field | MoPHP, UNICEF | MNPs scale up short guideline developed | Yes/No |  |  | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | x | x |  |  | Guideline developed | on track
| BSFP for PLW | MoPHP, WFP & Nutrition cluster partners | Number of PLW received BSFP | 60% of the case load in 158 districts that have access out of 165 -335,067 |  |  | 0 | 0 | 0 | BSFP database, WFP, NC Partners | 109283 | 72937 | 96093 | 6477 | 50277 | x | x | x | x | 361,151 PLW | • On track: 30% of annual caseload and 51% of annual target
| Iron-folate supplementation for PLW in coordination with BSFP | MoPHP, UNICEF and Nutrition Cluster partners | % of PLWs received Iron foliate supplementation in 213 districts | 70% of the case load in whole country -757,051 |  |  | 0 | 0 | 0 | CMAM database, CHVs database, outreach MTs database weekly database, Campaigns' databases | 147790 | 174304 | 154858 | 39947 | 240152 | x | x | x | x | 1,116,351 PLW | • On track: 100% of annual caseload reached | NC, UNICEF need to set together to calculate and adjust the caseload and Target
| Report BMS Code Violations (checking email, follow-up is needed, meeting took place with legal affairs, official letters sent to radio stations) | UNICEF, MoPHP, partners | Number of BMS code violations reported that were followed up | 100% |  |  | 0 | 0 | 0 | UNICEF email account for BMS code violations | 100% | 100% | 100% | 100% | 100% | x | x | x | x | one case reported on the internet. Nutritiion cluser/IYCF TWG follow up and partner stopped soliciting support | On track?
| Organise evaluation meeting on BMS Code Violations | UNICEF, MoPHP, WHO, partners | Number of meetings conducted | 2 |  |  | 0 | 0 | 0 | Cluster meeting minutes | N/A | N/A | N/A | N/A | N/A | x |  |  | x | 2 meetings held (March and June/July) | On track
| Conduct counselling of PLW and caregivers of children 0-23 months on IYCF | MoPHP, UNICEF, Nutrtion cluster partners | Number of PLW and caregivers of children 0-23 months received IYCF counselling | 70% of the case load - 1,682,335 |  |  | 0 | 0 | 0 | CMAM database , CHVs database, IYCF database and outreach MTs weekly database | 328422 | 387342 | 344129 | 88772 | 533670 | x | x | x | x | 1,414,823 PLW/Caregivers | • On track, 59% of annual caseload and 84% of annual target | double counting in the HF Corners and community?
| Develop a standard guideline for IYCF corners including supervision checklist | MoPHP, IYCF WG | Standard guideline for IYCF corners developed | Yes/No | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | N/A | N/A | N/A | N/A | N/A | x | x |  |  | Bending | Delayed
| Finalize MTMSG Guidelines | IYCF TWG | Guideline finalised and adopted | Yes/No | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | N/A | N/A | N/A | N/A | N/A | x |  |  |  | Integrated with the community health volunteers' package
| IYCF-E orientation/presentation at other clusters (heath, Nutrition, WASH, protection, NFI, FSAC) | IYCF WG, partners | Number of sessions conducted | 6 sessions at national level + 6*5 at sub-national | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | 6 | 6 | 6 | 6 | 6 |  |  | x |  | Pending. Planned for Q3 | Delayed
| Roll out SBC and APP strategy/Dissmination | SBC advisor, SAG, IYCF WG | SBC strategy developed and approved | Yes/no | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes | N/A | N/A | N/A | N/A | N/A | x | x |  |  | Pending | delayed | To be done 4th Quarter
Strengthen capacity of national authorities and partners to ensure effective decentralised nutrition response | CHVs training on CMAM / IYCF and key C4D messages. - 6 days (according to MoPHP current schedule) (Basic Training) | UNICEF, WFP, MoPHP, Nutrtion cluster Partners | Number of CHVs trained | 7,147 CHVs |  |  | 0 | 0 | 0 | Field Info template | [5 empty] | x | x | x | x | 1,489 CHVs have been trained | Delayed | Most of the training activities reports have not submitted, just some governorates submitted the reports
| CHVs training on CMAM / IYCF and key C4D messages. - Refresher Training) | UNICEF, WFP, MoPHP, Nutrtion cluster Partners | Number of CHVs trained | 16,659 CHVs | [5 empty] | Field Info template | [5 empty] | x | x | x | x | 5212 CHVs have been trained | On track | Most of the training activities reports have not submitted, just some governorates have been submitted the reports
| HWs training on CMAM (Refresher training) - 5 days | CMAM TWG | Number of people trained | 5,152 HWs |  |  | 0 | 0 | 0 | Field Info template | All CMAM, OTPs (at least once refresher per year for HWs) | All CMAM, OTPs (at least once refresher per year for HWs) | All CMAM, OTPs (at least once refresher per year for HWs) | All CMAM, OTPs (at least once refresher per year for HWs) | All CMAM, OTPs (at least once refresher per year for HWs) | x | x | x | x | 509 HWs have been trained | Delayed | Most of the training activities reports have not submitted, just some governorates have been submitted the reports
| Develop, revise and update national nutrition strategy and guidelines ( BSFP, MNP, CMAM, SMART survey, IYCF, MTMSG etc ) | MoPHP, UNICEF/WFP/WHO/ TWGs | Number of guidelines developed.revised/updated | 6 | [5 empty] | Strategy and guidenlinse developed | [9 empty] | 2 Finished, 1 ongoing | Delayed
| HWs training on CMAM (Basic training) - 10 days | CMAM TWG | Number of people trained | 1,813 HWs |  |  | 0 | 0 | 0 | Field Info template | 1 – 2 health workers per HFs. The # of HFs determined according to CMAM scale up plan. Cluster partners are included in the target group for this training | 1 – 2 health workers per HFs. The # of HFs determined according to CMAM scale up plan. Cluster partners are included in the target group for this training | 1 – 2 health workers per HFs. The # of HFs determined according to CMAM scale up plan. Cluster partners are included in the target group for this training | 1 – 2 health workers per HFs. The # of HFs determined according to CMAM scale up plan. Cluster partners are included in the target group for this training | 1 – 2 health workers per HFs. The # of HFs determined according to CMAM scale up plan. Cluster partners are included in the target group for this training | x | x | x | x | 2459 HWs have been trained | On track
| District monitors and districts assistants training on CMAM (Basic training) - 8 days | CMAM TWG | Number of people trained | 333 |  |  | 0 | 0 | 0 | UNICEF | All the new monitors and assistants | All the new monitors and assistants | All the new monitors and assistants | All the new monitors and assistants | All the new monitors and assistants | x | x | x | x | UNICEF/WFP to update
| Training of governorate level monitors and assistants on inpatient management of SAM (TFC/SC) - 8 days | CMAM TWG | Number of people trained | All governorates |  |  | 0 | 0 | 0 | WHO | All governorates | All governorates | All governorates | All governorates | All governorates | x | x | x | x | WHO to update
| HWs training on inpatient management of SAM (TFC/SC) (Basic training) - 8 days | CMAM TWG | Number of people trained | 760 HWs |  |  | 0 | 0 | 0 | Field Info, WHO | Targeted TFCs (50% of the staff) | Targeted TFCs (50% of the staff) |  | Targeted TFCs (50% of the staff) | Targeted TFCs (50% of the staff) | x | x | x | x | 692 HWs have been trained | On track
| HWs training on inpatient management of SAM (TFC/SC) (Refresher training) - 3 days | CMAM TWG | Number of people trained | 600 HWs |  |  | 0 | 0 | 0 | WHO | Targeted all old TFCs (46 TFCs) | Targeted all old TFCs (46 TFCs) |  | Targeted all old TFCs (46 TFCs) | Targeted all old TFCs (46 TFCs) | x | x | x | x | WHO to update
| SMART training for the local authorities (MoPIC, CSO, MoPHP) and partners - 5 days | AWG | Number of people trained | 80 People |  |  | 0 | 0 | 0 | Training Reports | 20 | N/A | N/A | N/A | N/A |  | x | x |  | Done in Aden 75 participants trained mostly GHOs. 6 NGOs trained | on track | Need for NGOs SMART training as most still requesting
| ToT for SMART manager trainers - 6 days | AWG TWG | Number of people trained |  |  |  | 0 | 0 | 0 | Training Reports | N/A | N/A | N/A | N/A | N/A |  | x
| Training on Data analysis for SMART - TBC | AWG TWG | Number of people trained |  |  |  | 0 | 0 | 0 | Training Reports | N/A | N/A | N/A | N/A | N/A | x | x
| nutrition Surveillance TOT |  | Number of people trained | 40 |  |  | 0% | 0% | 0% | WHO | N/A | N/A | N/A | N/A | N/A | x | x |  |  | Planned to be implemented in Septmber 2019 | Delayed
| nutrition Surveillance Basic |  | Number of people trained | 200 | [5 empty] | WHO | [9 empty] | Planned to be implemented in Novmber, 2019 after assessment of NSS | Delayed
| nutrition Surveillance Refresher |  | Number of people trained | 200 | [5 empty] | WHO | [9 empty] | Planned to be implemented in November, 2019 after assessment of NSS: | Delayed
| IYCF Training - Basic | UNICEF,MoPHP, Nutrtion cluster Partners | Number of people trained | 1619 |  |  | 0 | 0 | 0 | Field Info template | [5 empty] | x | x | x | x | 980 HWs/CMWs have been trained | on track | Most of the training activities reports have not submitted, just some governorates have been submitted the reports
| IYCF Training - Refresher | UNICEF,MoPHP, Nutrtion cluster Partners | Number of people trained | 1389 |  |  | 0 | 0 | 0 | Field Info template | [5 empty] | x | x |  |  | 240 HWs recieeved refresher training | on track
| IYCF-E - Basic | UNICEF,MoPHP, Nutrtion cluster Partners | Number of people trained | 62 | [5 empty] | Field Info template | [9 empty] | Pending
| Training of managers of hospitals and district managers, media on monitoring and reporting of the international code of BMS regulation - 1 day | MOPHP with support from IYCF WG | Number rof trainigns per governorate | At least one training per governorate |  |  | 0 | 0 | 0 | MoPHP records | [5 empty] | x | x |  |  | Pending
| Developmement of online nutrition information system | MoPHP, Nutrition Cluster Coordination team, UN agencies(UNICEF,WFP,WHO) | nutrition online information system developed | 1 | [14 empty] | x | New activity reacommened during the mid Year review
| conduct training to partners on nutrition information managmeent | UNICEF/WFP/nuttrition cluster | Number of people trained | 100 | [15 empty] | Done in Jan 2019. | 33 participants from NGOs partners trained | NC to conduct training and capacity development to MoPHP information management staff
| Support MoPHP nutrition graduate scholarship programme at Sanaa/Aden and institution | UNICEF, | Number of staff supported | one Year Diploma inside country in Sanaa and Aden instituts | Yes/No | [14 empty] | One batch already graduated, the second one will be graduated in September 2019 | Achieved
| Support MoPHP nutrition department with technical snd financial support | UNICEF. WFP | Number of departments supported | support provided | [15 empty] | Ongoing | On track
| Train partners on CMAM, based on the updated CMAM guideline | MoPHP/UNICEF/WFP | Number of partners trainied on new CMAM guideline
Ensure a predictable, timely and effective nutrition response through strengthening robust evidence based system and nutrition needs analysis and advocacy, monitoring and coordination | Conduct SMART surveys in all the 22 governnorates and in selected priority districts | AWG | Number of governorates where SMART surveys conducted | 22 |  |  | 0 | 0 | 0 | AWG meeting minutes | 8 | 4 | 2 | 2 | 6 | x | x | x | x | 9 Surveys conducted | On track | Most of SMART surveys be completed by October/Nov to provide inputs for HNO
| Conduct training on IPC for acute malnutrition for nutrition cluster partners in Yemen | NCC,FAO,UNICEF | Number of IPC for acute malnutrition conducted | one training in San'a and one in Aden | [15 empty] | One done in Sanaa, and Aden planned in October | On track
| Conduct joint IPC Acute Nutrition and Food Security analysis | AWG | IPC Acute malnutrition conducted | yes/no |  |  | 0 | 0 | 0 | AWG meeting minutes | N/A | N/A | N/A | N/A | N/A | x |  |  |  | Pushed to 4th Qtr October 2019 | Delayed | delayed due to challenging in logistic
| Develop intervention coverage gap analysis in consultation with partners and stakeholders at hub level. | MoPHP, UNICEF, WFP, WHO & Nutrition cluster partners | Number of Nutrition intervention coverage gap analysis | 2 | [13 empty] | x | x | New activity reacommened during the mid Year review
| Produce quarterly Nutrition Cluster Bulletin | NCC, IMO | Number of Bulletins produced | 4 |  |  | 0 | 0 | 0 | Number of bulletins on the website | N/A | N/A | N/A | N/A | N/A | x | x | x | x | First quarter done and posted on the cluster webpage | 2nd Qtr Delayed due to late submission of monthly reports
| Produce monthly analysis of nutrition data | IMO with support from AWG if needed | Number of monthly analysis of nutrition data produced at national and sub-national level | 12 |  |  | 0 | 0 | 0 | Number of monthly analysis on the website (national and sub-national levels) | N/A | N/A | N/A | N/A | N/A | x | x | x | x | Done on monthly basis and posted on the webpage | On track
| Conduct nutrition bottleneck analysis for Yemen | AWG + CMAM WG, led by UNICEF and MoPHP | Number of BNAs conducted | 2 |  |  | 0 | 0 | 0 | Workshop report |  | N/A | N/A | N/A | N/A | x | x |  |  | No update
| Conduct training on NIE | UNICEF,NC | Number of people trained | 46 |  |  | 0 | 0 | 0 | Cluster meeting minutes | [5 empty] | x | x |  |  | 5 Participants attended the updated NIE in Beirut | delayed- 4thQtr?
| Conduct Cluster Coordination performance monitoring exercise at national and sub-national levels | NCc and sub-national coordinators | Number of CCPM conducted and action plans developed | 1+5 | 0 | 0 | 0 | 0 | 0 | Cluster meeting minutes and CCPM reports | 1 | 1 | 1 | 1 | 1 |  | x | x |  | CCPM done in Ibb- but not completed. Other hubs to conduct CCPM before end of the year | particially on track | national normally done at the end of the Year
| Establish nutrition sentinel sites at health facility level in selected districts with focus on districts at risk of famine | MoPHP/WHO | Number of nutrition sentinel sites at health facility level setablished | 80 | [15 empty] | 40 Sites | On track
| Cluster coordination and information management training | NCc and sub-national coordinators and IMOs | NCCs - 7, IMOs - 6 | 7+6 |  |  | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | x | x | x | x | 3 cluster coordinators trained in Budapest | On track | In country training considered in 2020
| Conduct training on CMAM coverage assessment (SQUEAC) | WHO | Number of partners trainied on coverage | one training in San'a and one in Aden | [15 empty] | UNICEF/WHO to update