## 2023-24 workplan
GNC Climate working group workplan
| 2023 |  | 2024 |  |  |  | Lead | Support from Climate WG members | Comments
Activities | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
2023-24 Workplan - Oct 2023
1) Develop ToRs for the working group |  | Draft version |  | Updated version |  |  | Domi | All members + Diane
2) Mapping all climate-related projects/initiatives – including within the IASC cluster system – and ongoing climate and nutrition work with academia and research institutes. | [6 empty] | Diane with support from co-leads
3) Identify and approach organisations/individuals who are active on the climate/nutrition topic to become a member of the the Climate WG | [6 empty] | Domi and Andi with Diane's supports
4) Organise 4-5 webinars to raise awareness and create interest. |  |  | COP28 and NiE | [5 empty] | Specific tasks under this activity include: 1 - Select topics and identify lead(s) for each webinar. 2 - Develop agenda, identify subject matter experts, prepare communication materials to share information about the webinar with GNC and climate communities. 3 - Organise a debriefing session after each webinar to agree on follow-ups and next steps.
5) Further clarify the role of the Climate WG in support to countries and define ways of working with the helpdesk
New workplan - May 2024
WG management and ways of working
Update TORs to reflect composition and ways of working (engaging across GNC, with regions, with countries, eg task teams)
Continue expanding membership and technical network of regular members and resource persons, with intentional engagement to increase Global South engagement.
Update Working Group workplan to reflect priority actions from 2024 scoping, in coordination with GNC CT, GNC Programming Team, and GTWGs to ensure alignment.
Clarify/define ways of engagement for the working group with other relevant nutrition-climate platform/initiative including I-CAN (ATACH) and IASC Climate road map
Focus area 1: NIE climate lens in current approaches to nutrition risk analysis, preparedness and anticipatory actions. Focus for 2024: Integrated climate and nutrition risk analysis and Anticipatory Action in practice
Link with NIS GTWG for GNC needs analysis guidance and climate risk assessment for NIE (links with IASC climate roll out) with the view to develop a joint workstream on climate and nutrition risk analysis
Unpack further how to integrate Anticipatory Action within NIE, including establishing a task team, sharing and bringing together some good examples for webinar with country examples and development of interim guidance (link with OCHA led AA) | [7 empty] | Domi
Focus area 2: Climate-adapted NIE. Focus for 2024: socialization and evidence exchange on Climate & Nutrition pathways and implications for NIE programming and coordination
Socialise existing evidence on climate & Nutrition pathways (eg. webinar)
Lead on unpacking/deep dive on the care pathway (eg. commissioning a review of evidence and developing a brief on the care pathway in humanitarian contexts)
Focus area 3: Climate and environmental justice, anti-oppression, and localisation. Focus for 2024: increased Global South engagement in Working Group action and development of advocacy foundation through data analysis and oppportunity identification
Develop analysis of nutrition/NIE data and climate with focus area 3 lens ( e.g.; articulating multiple deprivations, climate and nutrition.) to support further advocacy, resource mobilization, prioritisation. | [7 empty] | Blanche
With the GNC CT and GNC Programming team, identify prioritized advocacy events (e.g. COP 29) where this analysis can inform key talking points.
Increase global south representation in the WG and in Task Teams for Working Group deliverables. (reflected in Ways of Working above) | [7 empty] | Blanche
Focus area 4: NIE climate and environmental impact mitigation. Focus for 2024: socializing current supply chain actions and identification of opportunities to better guage environmental impact at agency and collective levels
Take stock of GNC partner activities to mitigate climate and environmental impact of NIE programming, and identify mechanisms to continue regular exchange as activities develop (eg.; Entry points: Recipes, packaging, supply chain, storage, waste management) to support knowledge exchange. | [7 empty] | Valerie, Marie, Andi
Assess the relevance of developing a nutrition module for existing tools for environmental impact (eg NEAT+ tool)
Create a nutrition cluster/sector roadmap for decarbonization (including analysis of current GHG contributions). | [7 empty] | Valerie, Angeline | Alliance for the future of food; REH (Humanitarian Environmental Network); Climate center from IFRC
Support GNC capacity to undertake analysis of climate and environmental implications of NIE programming (eg. mapping tools/sharing tools/finding ways to reduce NIE impact) to support development of tools or guidance to use existing tools. | [7 empty] | Blanche
Focus area 5: support the GNC in NIE and climate crisis capacity
Create the GNC Climate and NIE webpage to support sharing & exchange with key resources (links to materials that are important) | [7 empty] | Angeline
Support to the GNC in its function supporting countries (support offer - tools and resources; working through with countries; proactive knowledge exchange)
Support update of GNC tools and resources with a climate lens (and upcoming tools) | [7 empty] | Angeline
Provide technical support to the GNC-CT in their involvement with the a) IASC roadmap for climate and b) Public Health Emergency Coordination and Response
Develop short NIE and climate learning brief | [7 empty] | Jess
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chair and co-chair put in sizable time in coordinating and doing the backend. Suggest you put in here.
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There are buckets, and within buckets focus areas for 2024. Do you want to keep buckets, and add this as a short description for that area of work? Since we have organized around buckets.
Note on A33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (link to nature based solutions in Sphere Unpacked 2018 guide for NbS) (link to articulation of NIE and climate crisis pathways, eg. what exactly is the Nutrition System's climate and environmental contribution through other systems, and making sure that it is adequately represented. And if there is anything over and above what is already in other systems, that it is articulated.
Note on A35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (perhaps building on existing tools; i.e. green house gas saved by Exclusive Breastfeeding; collaboration with developmental space - enviromental impact of diets from )